## Capital Projects
|  |  |  | Any Project between 300,000 and 500,000 can go to the BOG before BOT - per Sherry Ceallaigh's conversation with Phil on 3/14/2016 |  |  | REQUEST FOR CAPITAL PROJECT AUTHORIZATION |  |  |  | OC25 SUBMITTAL (REQUIRED TO SCO FOR PROJECTS OVER $2M ONLY) | [10 empty] | HAND OFF |  |  |  |  | REQUEST FOR DESIGNER/CONTRACTOR RATIFICATION/APPROVAL |  |  |  | REQUEST FOR INCREASE IN CAPITAL PROJECT AUTHORIZATION |  |  | DEBT/BOND ISSUANCE APPROVAL | PROJECT COMPLETE | GENERAL INFORMATION
Year | Project | Non-App Project | Approp. Project | Estimate/ Budget | Funding Source (s) | Schedule (CI-1 Form) | Date Approved by BOT FPPC | Dated Approved by Full Board | Budget Approved/ Reported | OC25 Completed but not submitted to SCO | OC25 Sent to SCO | OC25 Approved from SCO | Approved OC25 Amount | Sent to UNC System Office (BOG) | CI-1 | GA to (Gov Ops) BOG | Legislature (BOG Approval) | COS | Interscope Date | Interscope Amount | Code/Item | Scope | P6 Schedule | Cash Flow | Budget (Archibus) | Date | Date Designer/Consultant Approved/Ratified by BOT FPPC | Date Designer/Consultant Approved/Ratified by Full Board | Date Contractor Approved/Ratified by BOT FPPC | Date Contractor Approved/Ratified by Full Board | Date Approved by BOT FPPC | Dated Approved by Full Board | Budget Approved | Date Approved by BOT FPPC/Full Board | After Action Review (AAR) | Notes
2020 | Union Deck Elevator Replacement |  |  | 800000 | Aux Trust Funds - Parking Transportation | Design 6/2020; Construction 1/2021-7/2021 | 4/2/2020; 9/22/2020 | 2020-04-02 | 800000 |  | 2020-03-27 | [8 empty] | 800000 | 41926-310 | [13 empty] | x
2020 | Remembrance Memorial |  |  | $2,000,000 ($200,000 AP) | Campus Infrastructure Funds | Design 4/2020; Construction 2/2021-12/2021 | Req for Full Auth 4/6/2021 4/2/2020 | 4/6/2021 4/2/2020 | 2000000 |  | 2020-02-03 |  |  | 2/21/2020 for AP |  |  | 2020-02-21 |  |  | 200000 | 41926-309 | [14 empty] | Request for Full Authorization sent to April 6, 2021 BOT Meeting; April 6 Presentation: https://drive.google.com/file/d/1epDkc-Xcvknpe8ETcVADELlh7XgKUZ6K/view?usp=sharing
2019 | IT Infrastructure Upgrades (McEniry & Colvard Level 1000) |  |  | 3300000 | CFWD; E&T fee; Excess CID | McEniry work was combined with McEniry HVAC Upgrades | 2019-02-19 | 2019-02-19 | 3300000 | √ | 2019-01-24 |  | 3300000 | 3/22/19 BOG meeting | √ |  | 2019-03-22 |  | 2019-03-22 | 3300000 | 41826-305 |  | √ |  | √
2019 | McEniry HVAC Upgrades |  |  | 7700000 | Institutional Trust Funds | Design 12/2019; Construction 6/2020-9/2021 | 2019-10-02 | 2019-10-02 | 7700000 |  | 2019-10-11 |  |  | 2019-11-15 | [5 empty] | 7700000 | 41926-302 |  | √
2019 | Energy Projects Phase II |  |  | 1000000 | CFWD | Design 7/1/2019; Construction 1/15/2020-8/15/2020 | 2019-02-19 | 2019-02-19 | 1000000 | √ | 2019-01-24 |  |  | 3/22/19 BOG meeting | √ |  | 2019-03-22 | [5 empty] | √
| Campus-wide Amenities Upgrade |  |  | 0 | [6 empty] | U 9/29/2010 | U 9/29/2010 | 1281000 | 2010-09-29 | [21 empty] | 2010 6 yr R&R Submitted 9/29/10
| Campus-wide Code Corrections |  |  | 0 | [6 empty] | 2010-10-27 | 2010-12-20 | 2851000
| Campus-wide Door Replacement |  |  | 0 | [6 empty] | U 9/29/2010 | U 9/29/2010 | 639000 | 2010-09-29 | [21 empty] | 2010 6 yr R&R Submitted 9/29/10
| Campus-wide Elevator Repairs/Replace |  |  | 0 | [6 empty] | 2010-10-27 | 2010-12-20 | 1983000
| Campus-wide Elevator Upgrades |  |  | 0 | [6 empty] | 2010-10-01 | 2010-10-28 | 2090000 | 2010-09-29
| Campus-wide HVAC Improvements |  |  | 0 | [6 empty] | 2012-08-16 |  | 2000000 | [22 empty] | RR11 & RR12
| Campus-wide Infrastructure |  |  | 0 | [6 empty] | 2010-10-27 | 2010-12-20 | 4700000
| Campus Infrastructure Renewal DUPLICATE - REMOVE/SHERRY |  |  | 2150000 | CFWD 13 |  | 2014-02-28 |  | 2150000 |  |  |  |  | 3/2014 |  |  | 4/2014 |  | 2014-04-11 | 2150000 | 41326-309 | [14 empty] | Duplicate project - Delete
2019 | Starbucks Renovation |  |  | 485000 | Dining Receipts | Design 12/20/2019; Construction 5/16/2020-7/20/2020 | 2019-10-02 | 2019-10-02 | 700000 |  | 2019-11-20 | [8 empty] | 700000 | 41926-307 |  | √ | [11 empty] | √
2019 | Cameron 2nd Floor Renovation |  |  | 19100000 | CFWD | Design 7/15/2019; Construction 9/1/2020-7/1/2021 | 4/12/2019 Advance Planning | 4/12/2019 Advance Planning | $1,950,000 (only AP is authorized) | √ |  |  |  | 2019-05-21 | √ |  | 2019-05-22 |  | 2019-05-21 | 1950000 | 41826-306 |  | √ |  | √ |  | 2019-10-02
| Campus-wide Generator Upgrades |  |  | 1200000 | CFWD 13 | Design: Jan. 2015; Const.: June 2016 - 10/2016 | NA |  | 1200000 |  |  |  |  | 2013-12-19 | √ |  | 1/10/2014 |  | 2014-01-10 | $1.2 M | 41326/306 |  | N/A |  | N/A | [10 empty] | Shops are completing project/Sherry Update
| Campus-wide PACE Initiative Energy Project HVAC System analysis & energy savings |  |  | 0 | [6 empty] | 2010-10-27 | 2011-02-18 | 6400000
| Campus-wide Repair Walls & Foundations |  |  | 0 | [6 empty] | U 10/27/2010 | U 10/27/2010 | 907000
| Campus-wide Retro Commissioning |  |  | 0 | [6 empty] | U 9/29/2010 | U 9/29/2010 | 1643000 | 2010-09-29 | [21 empty] | 2010 6 yr R&R Submitted 9/29/10
| Campus-wide Storm Drainage Upgrade |  |  | 0 | [6 empty] | U 9/29/2010 | U 9/29/2010 | 500000 | 2010-09-29 | [21 empty] | 2010 6 yr R&R Submitted 9/29/10
2019 | New CRI Entrance Road |  |  | 1500000 | CID Fee | Design 1/2020; Construction 6/2020-1/2021 | 2019-10-02 | 2019-10-02 | 1500000 |  | 2019-10-16 |  | 1500000 | 2019-11-15 | [5 empty] | 1500000 | 41926-303 |  | √
| CID 1-Street Lighting Upgrade for Efficiency - Moved to Utility fund and not CID 1 |  |  | 436000 |  |  |  | 2019-10-03
2019 | Parking Lot 5A Expansion |  |  | 1000000 | Parking Receipts | Design 1/2020; Construction 4/2020-8/2020 | 2019-10-02 | 2019-10-02 | 1000000 |  |  |  | 1000000 | 2019-11-15 | [5 empty] | 1000000 | 41926-301 |  | √ |  |  |  | 2020-04-02 | [8 empty] | Project to be on hold 2021 January
| CID II Project A -Colvard Remaining Projects - moved out of CID |  |  | 24156.79 | CFWD 13, 14, CID 2A, 2B |  |  | 2019-10-05 |  |  |  |  | N/A | [13 empty] | 2020-04-03 | 2014-10-02 | [7 empty] | Moved out of CID into own project
| CID 1 Project - Hauser Alumni Pavilion Sewer |  |  | 390000 | CID 1 | Const.: 7/2016- 9/2016 |  | 2019-10-06 | [18 empty] | 2020-04-04
2019 | Fretwell Café Renovation |  |  | 900000 | Dining Receipts | Design 1/2020; Construction 6/2020-8/2021 | 2019-10-02 | 2019-10-02 | 900000 |  |  |  | 900000 | 2019-11-15 | [5 empty] | 900000 | 41926-304 |  | √ |  |  |  | 2020-04-02
| CID II Project - East Village Infrastructure, PH 1 & 2 - combined with 3 & 4 (City contribution added to Interscope on 10/21/2016 - $2,150,000 |  |  | 7100000 current authorization $5,536,825 | CID 2A | Design: Apr 2014; Phase 1 traffic improvements: Const. 3/12/2019-6/1/2020 |  | 2019-10-08 |  |  |  |  | N/A | [8 empty] | √ | √ | √ | √ |  | 2020-04-06 | 2014-10-02
[8 empty] | 2019-10-09 | [18 empty] | 2020-04-07
| Burson Building Modernization & Expansion |  | X | 34320000 |  |  | 2008-11-13 | 2019-10-10 | 34320000 |  | 10/1/2010 11/3/2008 | 10/28/2010 11/6/2008 | $76,000,000 $67,600,000 | 2010-09-15 | [12 empty] | 2020-04-08 | [8 empty] | 6 yr Approp Submittal 9/15/10 / CCD 6/17 ; Total has changed and moved to CID 2 due to new Science Bldg.
2019 | Popp Martin Student Union Dining Renovation |  |  | 11498950 | Dining Receipts | Design 5/2020; Construction 5/2020-8/2020 | 2019-10-02 | 2019-10-02 | 11498950 |  | 2019-11-06 |  | 11498950 | 2019-11-15 | [5 empty] | 11498950 | 41926-305 |  | √ |  |  |  | 2020-04-02
| CID II Project F - East Village Utilities |  |  | 2100000 | CID 2B | Const.: 10/2016 - 3/2017 | [20 empty] | 2020-04-10 | N/A | [7 empty] | Combined with phase 1 & 2/Sherry Update
| CID II Project H - Campus-wide Road Improvements phase 2 (this is now included in CID 1 |  |  | 3398175 | CID 2B | [16 empty] | √ | √ | √ | √ |  | 2020-04-11
| Cone Plaza Repairs IN CONSTRUCTION |  |  | 1600000 | Carry Forward |  | 2012-04-26 | 2012-04-26 | 1600000 |  | 5/10/2012 U 9/29/2010 | U 9/29/2010 | $1,600,000 $545,000 | 1/8/14 3/26/2012 |  |  | 2012-04-03 |  | 1/8/14 4/24/2012 | $2,254,880 1,600,000 | 41126/307 | [5 empty] | 2020-04-12 | [8 empty] | PJ emailed SCO ID#12-09714-01
| Colvard HVAC Upgrade & RUP |  | X | 0 | [6 empty] | U 10/27/2010 | U 10/27/2010 | 1000000 | [13 empty] | 2020-04-13
| Colvard Building Modernization |  |  | 0 | [6 empty] | 2012-08-16 |  | 1584200 | [13 empty] | 2020-04-14 | [8 empty] | FY11 RR
| Cone Center Food Service Renovation - Design Services Project |  |  | 491800 | Dining Receipts Fund Balance (Cash on hand) | Design Start 1/15/2015; Construction Start; 5/25/2015 |  | Per Phil - not needed: 10/2015 - report only | [5 empty] | 2015-04-21 | √ |  | 2015-05-22 |  | 2015-05-22 | 491800 | 41426-314 |  |  |  |  | N/A | 2020-04-15 | [8 empty] | Design Services Project
2019 | Science Café |  |  | 1500000 | Dining Receipts | Design 1/2021; Construction 1/2021-7/2021 | 2019-10-02 | 2019-10-02 | 1461631 |  | 2019-10-11 |  | 1461631 | 2019-11-15 | [5 empty] | 1461631 | 41926-306 |  | √ |  |  |  | 2020-04-02
2019 | J.W. Clay Boulevard and Robert D. Snyder Road Modifications |  |  | 1000000 | CID Fee |  | 2020-04-02 | 2020-04-02 | 1000000 | [7 empty] | 2019-12-13 |  |  | 1000000 | 41926-308 |  | √ |  |  |  | 2020-04-02
| Energy Savings Performance Contract |  |  | 0 | [14 empty] | 2012-10-03 | 8500000 | 41226-370 | √ | √ | √ | √
| Fire Detection System Upgrade - Belk Gym, Belk Track, Burson, Cafeteria, Cameron, Cato, Cone, Central Plant, Prospector, RDH, Wachovia Field House |  |  | 0 | [6 empty] | U 10/27/2010 | U 10/27/2010 | 1730000
2018 | Intercollegiate Swimming Renovation |  |  | 3500000 | Student Fees | Design: 7/15/2018; Const.: 5/1/2019 - 3/15/2020 | 2018-10-02 | 2018-10-02 | 3500000 | √ | 3/22/2018 resubmitted 6/11/18 | 2018-06-11 | 3500000 | 2018-03-22 | √ |  | 2018-05-24 |  | 2018-06-11 | 3500000 | 41726-307 | √ | √ | √ | √ |  | 2018-10-02 | 2018-10-02
| Flats 1 & 2 |  |  | 0
| Football Complex Expansion | X |  | 0 | [6 empty] | 2010-10-27 | 2010-12-20 | 60000000
| Football Exterior Lighting | X |  | 2.5M | stadium fee | const 2015 | 2013-05-23 | 2013-05-23 | 2.5M |  | 5/16/13 10/27/2010 | 2010-12-20 | $2.5M $2M | 2013-12-19 | √ | 1/10/2014 | 1/10/2014 |  | 2013-08-07 | 2500000 | AP41226/311; AP41226/311 | [14 empty] | Construction complete by 8/15
| Friday - New Sprinkler System |  | X | 0 | [6 empty] | U 10/27/2010 | U 10/27/2010 | 610000
| Friday and Fretwell HVAC Updgrade |  | X | 0 | [6 empty] | 2010-10-01 | 2010-10-28 | 2230000 | 2010-09-29 | [21 empty] | 2010 6 yr R&R Submitted 9/29/10
| Hawthorn Lobby - SCOPE DECREASE - REMOVE FROM BOT AND BOB |  |  | 493000 | Housing and Resicence Life Dining Receipts | Design: May 2016; Construction: June 1, 2016; Complete: August 2016 | 2016-04-28 |  | 493000 |  |  |  |  | 2016-04-15 |  |  | 2016-05-27 | [18 empty] | SCOPE DECREASE - REMOVE FROM BOT AND BOB
| Holshouser Renovation (IN CONTRUCTION) | X |  | $17,600,000 12,595,208 |  | Const start 5/14;CCD 7/15 | 12/5/2013 12/10/2010 | 12/5/2013 12/10/2010 | $17,600,000 12,595,208 |  | 5/6/14 5/7/13; 10/27/2010 | 5/14/2013 12/7/2010 | $19.5 M; $16M; 12,595,000 | 2012-07-19 | √ | 2012-07-20 | 6/14/13; 7/20/2012 |  | 7/15/2014 9/11/2012 7/20/2012 | $19.5 M; 1,259,520 125,952 | AP41226/305 | x | √ |  | x | 2013-05-07 |  |  | 2013-05-23 | 2013-05-23 | 5/23/13 BOT | 5/23/13 BOT | 17600000 |  |  | $16 M - May 13 BOT
| Lecture Hall Improvements-Rowe Arts Bldg. |  | X | 1500000 |  |  | 2006-06-23 | 2006-06-23 | 1500000 |  | 2007-09-10 | 2007-09-13 | 1500000
| McEniry and Colvard Teaching Modernizations |  | X | [7 empty] | 2010-10-01 | 2010-10-28 | 5643000 | 2010-09-29 | [21 empty] | 2010 6 yr R&R Submitted 9/29/10
2018 | Bioinformatics 4th Floor Upfit |  |  | 6000000; $11,500,000 | Institutional Funds | Design: 7/15/2018; Const.: 10/24/2020 - 7/20/2021 | 2018-10-02 | 2018-10-02 | 11500000 | √ | 3/22/2018 resubmitted 6/8/18 | 2018-06-11 | 11500000 | 12/?/2021 3/22/2018 | √ |  | 1/?/2022 5/24/2018 |  | 2018-05-31 | 11500000 | 41726-306 | √ | √ | √ | √ |  | 2019-10-02
| Kennedy Emergency Generator |  |  | 500000 | Institutional |  | 2014-12-04 | 2014-12-04 | 500000 |  |  |  |  | 2014-11-07 | √ |  | 2014-12-05 |  | 2014-12-05 | 500000 | 41426 - 308 | [14 empty] | Handed off to Design Services
| Irwin Belk Track Resurfacing |  |  | 1400000 $1,850,000 | Athletic Foundation reserves | Design: 12/15; Const: 5/16 - 10/16 | 12/3/2015 10/6/2016 (Report only since after the fact) | 2015-12-03 | 1400000 $1,850,000 | √ |  |  |  | 10/30/2015 9/9/2016 | √ |  | 12/11/2015 10/14/2016 |  | 12/11/2015 10/14/2016 | 1400000 $1,850,000 | 41526-304 | √ | √ | √ | √
| Modular Office Building (MOB) |  |  | $950K |  |  | 2013-05-23 | 2013-05-23 | $950K |  | 2013-05-16 | U 5/16/13 | 950000 |  | X | 2013-05-01 | 2013-06-14 |  | 2013-06-14 | 950000 | AP41226/310 | [14 empty] | $950K. - Complete
2018 | IT Infrastructure Upgrades (Rowe, Storrs, Reese) |  |  | 3800000 | Institutional Funds | Design 12/1/18; Construction 11/3/2019 - 3/1/2020 | 2018-10-11 | 2018-10-11 | 3800000 | √ | 2018-08-14 | 2018-10-09 | 3800000 | 2018-07-13 | √ | 2018-09-14 | 2018-10-10 |  | 2018-10-09 | 3800000 | 41826-303 |  | √
| Music Annex (IN CONSTRUCTION) |  |  | $3 M | Others |  | 2013-10-10 | 2013-10-10 | $3 M |  | 2014-01-31 | 2014-02-05 | 3000000 | 1/14/2014 | √ |  | 1/10/2014 |  | 2014-01-10 | 3000000 | 41326/305
| New Residence Dining Hall (Residence Dining Hall Replacement-South Village) (IN CONSTRUCTION) | X |  | 20330000 |  |  | 2010-02-05 | 2010-02-05 | 20330000 |  | 2010-10-27 | 2010-12-20 | 29177000 |  |  | 2011-07-07 | 2011-07-07 |  | 9/23/2011 7/29/2011 8/5/10 | 31,209,738 29,176,738 2,033,000 | AP41026/304 41126/303 | [5 empty] | 2011-02-17 | 2011-02-17 | 2011-04-28 | 2011-04-28 | 5/23/13 BOT |  |  | 2011-12-08
| Oak Hall Renovation (IN CONSTRUCTION) |  |  | 9000000 |  | Const start 5/14;CCD 7/15 | 2012-04-26 | 2012-04-26 | 9000000 |  | 2012-08-16 | 2012-12-06 | 8900000 | 2012-07-19 | √ | 2012-07-20 | 6/14/2013; 7/20/2013 |  | 9/11/2012 7/20/2012 | 890,000 89,000 | AP41226/304 | √ | √ |  | √ | 2012-09-26 | 2013-05-23 | 2013-05-23 | 2013-10-10 | 2013-10-10 | [5 empty] | Designer 5/23/2013
| Outdoor Event Shelter |  |  | 1,600,000 1200000 | Operationl costs: Facilities Usage Charges | Design 11/1/2014; Const start 4/1/2015 | 4/23/2015; 12/4/2014 | 2014-12-04 | 1200000 |  |  |  |  | 3/12/2015 - increase; 11/7/2014 | √ |  | 2014-12-05 |  | 2014-12-05 | 1200000 | 41426 - 309 | √ | √ | √ | √ | √
| Parking Deck J (CID Project-RUP 4 only) | X |  | 27418000 |  |  | 2010-02-05 | 2010-02-05 | 27418000 |  | 2010-02-08 | 9/27/2011 2/26/2010 | 27418000 | 2010-01-10 |  | 2010-04-01 |  |  | 9/23/2011 7/29/2011 8/5/2010 | 30,159,800 27,418,000 2,741,800 | 41026/305 41126/304 AP 41026/305 | [5 empty] | 4/2//11 | 2011-04-28 | 2012-04-26 | 2012-04-26 |  |  |  | 2011-12-02 | 2014-08-12 | CCD 7/13; RUP CCD 5/13
2018 | Roof Repairs and Replacement - Various Buildings |  |  | 1300000 | R&R | Design 7/1/18; Construction 5/13/2019 - 8/11/2019 | Annual R&R Funds, did not go to BOT | Annual R&R Funds, did not go to BOT | 1300000 | √ | 2018-12-19 | 2018-12-20 | 1300000 | 9/3/2020 Annual R&R Funds, did not go to BOG |  |  | Annual R&R Funds, did not go to BOG |  | 2018-09-11 | 1300000 | 41826-320 | √ | √ | √ | √ |  | 2019-02-19 | [8 empty] | 9/3/2020 - McEniry Roof Replacement RFP Submitted to GA and UNCC Websites
| PORTAL (i.e.,CRI Collaborative Research Buidling) - COMPLETE | X |  | 50000000 $35,000,000A |  |  | 2008-01-31 | 2008-01-31 | 50000000 $35,000,000A |  | 3/18/2009 8/5/2008 | 6/15/2009 9/16/2008 | $30,718,000 $35,000,000 $54,147,867.46 | [5 empty] | 4/26/2011 9/22/2009 9/28/2008 | 37,700,000 40,000,000 35,000,000 | 40826/303 40926/302 | [5 empty] | 2009-04-16 | 2009-04-16 | 2009-12-11 | 2009-12-11 |  |  |  | 2011-12-08 |  | CCD 4/14 / Accepted 1/28/14
| Reese Building Renovations |  | X | 0 | [6 empty] | 2010-10-01 | 2010-10-28 | 2486000 | 2010-09-29 | [21 empty] | 2010 6 yr R&R Submitted 9/29/10; Reese
| 2011/2012 Repairs and Renovations $2,610,500 - COMPLETE |  |  | 0 | [11 empty] | ? |  |  | 2011-07-01 | 2610500 | 41126-320
| 2011/2012 R & R - |  |  | 3309700
| HVAC Phase 1 - Complete |  |  | 210500
| Colvard Renovation (2000 level) - COMPLETE |  |  | 3099200 | [6 empty] | 2013-05-06 | 2013-05-10 | 2366000 | [8 empty] | √ | √ |  | √ |  | 2013-10-10 | 2013-10-10
| Campus-wide Roof Replacements (COMPLETE) |  |  | 1793379
| Colvard Building 2nd Floor Renovation Phase III |  |  | 500000 | [31 empty] | Funds transferred back to the original project in 2011 R & R
| Reese Building Foundation and Window Repairs |  |  | 903200 | R & R
| Residence Hall Phase X - COMPLETE | X |  | $31,045,802 $51,565,000 | HRL |  | 2010-02-05 | 2010-02-05 | $31,045,802 $51,565,000 |  | 10/1/2010 11/3/2008 | 10/28/2010 11/4/2008 | $31,046,000 $51,564,645 | 2010-01-10 |  | 2010-04-01 |  |  | 9/23/2011 7/29/2011 8/5/2010 8/5/2010 | 34,102,302 31,045,802 5,156,500 3,056,500 | 41026/303 41126/301 AP 41026/303 | [5 empty] | 2010-12-10 | 2010-12-10 | 2010-12-10 | 2010-12-10 |  |  |  | 2011-12-08 | 2014-04-07 | CCD 8/13
| Residence Hall Phase XI | X |  | 40837005 | HRL |  | 2010-12-10 | 2010-12-10 | 40837005 |  | 2010-10-01 | 2010-10-28 | 40837000 | 2010-09-29 |  |  |  |  | 9/23/2011 7/29/2011 10/13/2010 | 42,937,005 40,837,005 2,100,000 | 41026/307 41126/302 AP 41026/307 | [5 empty] | 2010-12-10 | 2010-12-10 | 2010-12-10 | 2010-12-10 |  |  |  | 2011-12-08 | 2014-05-20 | CCD 6/13
| Campus Wide Roof Replacement |  |  | 2293380
| Residence Hall Phase XII (East Village Sector Study) CLOSE OUT | X |  | 38407410 | HRL |  | 2010-12-10 | 2010-12-10 | 38407410 |  | 2010-10-27 | 2010-12-20 | 38407000 | 2011-11-29 |  | 2012-04-13 | 2012-04-13 |  | 8/13/2012 7/1/2012 7/29/2011 | $42,248,151 $38,407,410 $3,840,741 | 41126/305 41226/302 AP 41126/305 | [5 empty] | 4/26/2012 AP7/7/11 | 2012-04-26 | [5 empty] | 2012-09-06 |  | CCD 8/14
2018 | HVAC System Repairs and Upgrades - McEniry |  |  | 500520 | R&R | Design 9/27/18; Construction 3/1/2019 - 5/31/2019 | Annual R&R Funds, did not go to BOT | Annual R&R Funds, did not go to BOT | 500520 | √ | 2018-10-24 | 2018-10-24 | 501000 | Annual R&R Funds, did not go to BOG |  |  | Annual R&R Funds, did not go to BOG |  | 2018-09-11 | 500520 | 41826-321 | √ | √ | √ | √
| Sycamore Hall Renovation (see Sycamore Hall Renovation Project Listed below - this is just partially funded by R & R.) |  |  | Partially Funded R&R: $889,667
2018 | Lab School Renovations |  |  | 1000000 | R&R | Design 12/1/2018; Construction 4/1/2019-8/1/2019 | Annual R&R Funds, did not go to BOT | Annual R&R Funds, did not go to BOT | 1000000 | √ | 2018-09-07 | 2018-09-07 | 1000000 | Annual R&R Funds, did not go to BOT |  |  | Annual R&R Funds, did not go to BOT
| Residence Hall Phase XIV | X |  | $49,000,000 31711245 | HRL | Const start 11/14;CCD 7/16 | 4/3/14 12/10/2010 | 2010-12-10 | $49,000,000 31711245 |  | 2/3/14 10/27/10 | 2/24/2014 12/20/2010 | $49,000,000 31711245 | AP 5/15/13 | √ | 2013-05-15 | 2014-02-21 |  | 2013-05-15 | $45,829,000 3171120 | AP 41226/309 | √ | √ |  | √ | 2013-06-03 | 2013-10-10 | 2013-10-10 | 2013-12-05 | 2013-12-05 | [5 empty] | Suites
| Residence Hall Phase XV - CANCELLED | x |  | 44293200 | HRL | Const start 7/15;CCD 7/17 | 4/14 10/10/2013 | 2013-10-10 | 44293200 |  |  |  |  | 2014-01-15 | x |  |  |  | 1/15/2014 | 4429320 | AP 41326/308 |  | √ | [12 empty] | $44,293,200; CCD 7/17; Apt. @ Martin; CANCELLED
| Roof Replacement-Barnard & Garinger COMPLETE |  | X | 0 | [6 empty] | U 10/27/2010 | U 10/27/2010 | 919000
2018 | Sanford Hall Renovation - | X |  | $30,000,000; $19,000,000 13500000 | HRL | Construction: 5/2020 to 7/2021 | 10/2018; 4/3/14 12/10/2010 | 2012-09-06 | $30,000,000; $19,000,000 13500000 | √ | 2/3/14 10/27/10 | 2/6/14 12/20/2010 | $19,000,000 13500000 | 11/?/18; 9/18/2012 | √ |  | 12/?/2018; 2/21/2014 |  | 2012-09-19 | $30,000,000; $19,000,000;1350000 | 41226/308 | [5 empty] | 2013-10-10 | 2013-10-10 | 2013-12-05 | 2013-12-05 | [5 empty] | 9/19/12 GA approved AP - 6/15 Const. Start; Self liquidating bill 2014
2018 | Campus Infrastructure Phase 3 |  |  | 1829547 | non-general fund/R&R general funds | 5/30/18 - 1/10/19 |  |  |  | √ | 2013-06-30 | 2013-07-01 | 6,415,875 (multiple programs) |  |  |  | 2013-07-01 |  | 2013-07-01 | 6,415,875 (multiple programs) | 41726-320 |  | √
2017 | Residence Hall Phase XVI |  |  | $64,500,00 58500000 | Housing Fund Balance (42%) / Housing Receipts (58%) | Const. 5/14/2018 - 7/2/2022 | 2017-11-28 | 2017-11-28 | 58500000 | √ | 2018-02-27 |  | 58500000 | 2018-02-27 | √ |  | 12/18/2019; 3/23/2018; 12/15/2017 |  | 2017-12-12 | 58500000 | 41726-302 | √ | √ | √ | √ |  | 2018-02-15 | 2018-02-15 | 2018-02-15 | 2018-02-15
2017 | Softball Indoor Training Facility |  |  | 650000; 1,150,000 increase requested 1/30/2018; 1,250,000 | Athletic Foundation, Gifts | Design: 6/1/2017 9/6/2017; Const. 12/1/2017 - 4/30/2017 7/2018 - 1/2019 | 2017-04-20 | 2017-04-20 | 650000; 1,150,000 increase requested 1/30/2018 | √ | 1/30/2018; 3/22/2018 | n/a | n/a | 3/21/2017; 3/22/2018 | √ |  | 2017-05-19 |  | 2017-05-22 | 1250000 | 41626-310 | √ | √ | √ | √ | [10 empty] | increase request on 01/30/2018
| South Entrance Roadway Improvements |  |  | $3.5 M | CFWD 14 |  | 2013-10-10 | 2013-10-10 | $3.5 M |  | 2013-05-16 |  |  | 2014-02-01 |  |  | 2014-04-01 |  | 2014-04-11 | 3500000 | AP 41326-310 | √ | √ | √ | √ | [10 empty] | $3.5M; Design funded by CID.
2017 | Student Government Office Renovations |  |  | 1200000 | Student Union Fee Receipts | Cont. 9/29/2019- 1/26/2020 | 2017-11-28 | 2017-11-28 | 1200000 | √ | 2018-02-11 | 2018-02-12 | 1200000 | 2017-12-15 | √ |  | 2017-12-15 |  |  | 1200000 | 41726-305 |  | √
| Student Academic Success & Retention - FUTURE |  |  | 0 | [31 empty] | BOG 3/6/12-$94,700,000
| Student Activity Center (SAC) Fitness Center Renovation - Design Services |  |  | 489650 | Student Recreation Fee Fund Balance (Cash on hand) | Design 11/14/2014; Construction 5/23/2015 |  | Per Phil not needed: 10/2015 (Report only) | [5 empty] | 2015-04-21 | √ |  | 2015-05-22 |  | 2015-05-22 | 489650 | 41426-313 |  |  |  |  | N/A | [9 empty] | Design Services Project
2017 | Atkins Air Handler (AHU) |  |  | 1600000 | Carry Forward | Const. 12/2018 - 7/2019 |  |  | 1600000 | √ | 2017-12-12 | 2017-12-12 | 1600000 | 2017-11-03 |  |  | 2017-12-12 |  | 2017-12-13 | 1600000 | 41726-303 | √ | √ | √ | √
2017 | Student Activity Center (SAC) IT Upgrade |  |  | 1800000 | Excess SAC Debt Fee | Const. 3/2018 - 1/2019 | 2017-02-09 | 2017-02-09 | 1800000 | √ | 2017-03-13 |  |  | 2017-01-13 |  |  | 2017-03-03 |  | 2017-03-03 | 1800000 | 41626-307
| New Warehouse Facilities (SDI, Receiving and Stores, etc.) (?) NOW INCLUDED IN FO COMPLEX |  |  | 2500000 |  | Design: Nov 2016; Const.: Nov2018 | [29 empty] | NOW INCLUDED IN FO COMPLEX
2017 | Moore Residence Hall Renovation - | X |  | $28,500,000 15,750,000 |  | Construction: 5/2019 to 7/2020 | 10/2017 10/10/2013 | 2013-10-10 | $28,500,000 15,750,000 | √ | 2010-10-27 | 2010-12-07 | 15750000 | Full Authorization: 11/3/2017; 5/20/2014 |  | 2014-06-20 | 12/15/2017; 6/20/2014 |  | 2014-06-20 | $28,000,000 $2,068,a755 | AP41326-312 | √ | √ | √ | √ |  | 2017-10-11 | 2017-10-11 | [7 empty] | 6/16 Construction Start
| Hotel Site Land Disposition |  |  | no cost land disposition | [9 empty] | 2018-05-23 |  |  | 2018-05-24
| NCRC Land Acquisition by Lease |  |  | 922778.69 | [9 empty] | 2018-05-23 |  |  | 2018-05-24
2016 | Campus Circulation Improvements (Light Rail Complimentary Projects) |  |  | 1000000; $1,400,000 approval rec'd 5/24/18 | Excess CID Debt Fee F & A (Facilities & Administrative Receipts) | Design: 6/13/2016; Constr.: Mar. 8/30/2017 - Jun 2017 12/15/2018 | 2016-02-19 | 2016-02-19 | 1000000 | √ | 2018-03-22 | 2018-03-22 | 1400000 | 1/22/2016 3/22/2018 | √ |  | 2016-03-04 |  | 2016-03-14 | 1000000 | 41526-310 | √ | √ | √ | √ | 2016-03-09
2016 | Reclaimed Water Project |  |  | 2100000 | Utility Savings | Const: 3/31/2020 - 7/28/2020 | 2016-10-06 | 2016-10-06 | 2100000 | √ | 2018-07-26 | 2018-07-26 | 2100000 | 2016-12-02 |  |  | 2017-01-13 |  | 2017-01-17 | 2100000 | 41626-305 |  | √ |  |  |  | 2017-10-11 | 2017-10-11
2016 | West Substation |  |  | 6500000 | CFWD/F & A | Design: 9/16 12/1/16, Const: 3/29/2020 - 3/28/2021 | 2016-02-19 | 2016-02-19 | 6500000 | √ | 2018-08-07 | 2018-08-07 | 6500000 | 1/22/2016 5/23/2018 | √ |  | 3/4/2016; full authorization approved 7/27/18 |  | 2016-03-04 | 6500000 | AP41526-309 | √ | √ | √ | √ | 2016-03-16 | 2016-11-30 | Report only | [7 empty] | Project to be on hold 2021 January
2016 | Science Building (2/3 of new RUP and site demo included in Science bdgt.; Data Center added 7/2016) |  | X | $101,000,000 90,000,000 120000000 | NC Bond/F&A Excess CID Debt Fee | Design: 8/2016; Const: 2/23/2018 - 2/25/2021 | Increase: 7/1/2016 11/13/2008 | 2008-11-13 | 101,000,000 90,000,000 120000000 | √ (revised 5/2016) | 9/15/2010 8/5/2008 | 2008-09-16 | 126383374.52 | Increase 7/1/2016 9/15/2010 |  | AP 3/6/12 | 1/26/2018 9/9/2016; 1/23/2018 (demo.) |  | 3/15/2016 3/6/2012 | 101,000,000; 90,000,000 $12,638,337 | 46626-301 | √ | √ |  | √ | 2016-05-05 | 2016-10-06 | 2016-10-06 | 2017-02-09 | 2017-02-09 | [5 empty] | 2/2012-Request to GA; Money was returned. Bond Approval slated for March 2016 approval. (RUP) Regional Utility Plant: Beneficial occupancy approved 10/29/2020; Contract completion 11/10/2020
2016 | Campus Regional Storm Water Master Plan Improvements Phase 2 (Toby Creek) |  |  | 750000 $850,000 | Capital Contingency Reserve | Design: 1/2017; Const.10/10/2019 - 10/9/2020 | 2016-10-06 | 2016-10-06 | 850000 | √ | n/a | n/a | n/a | 2016-10-09 |  |  | 2016-12-02 |  | 2016-12-05 | 850000 | 41626-304 | √ | √ | √ | √ | [10 empty] | *Per John Fessler - only $750,000 needed.
2013 | East Village Infrastructure Phase IV |  |  | 5536825 | CID2 | Const. 3/12/2019 - 6/1/2020 | 2013-05-23 | 2013-05-23 | 7866825 | √ | 2014-06-01 | 2014-06-02 | $54,530,335 (multiple programs) |  |  |  | 2013-01-15 |  | 2013-01-15 | $54,530,335 (multiple programs) | 41326-307 | √ | √ | √ | √ |  |  |  | 2019-02-15 | 2019-02-15 | [5 empty] | 8/31/2020 - Plans submitted to SCO (2nd CD submittal) 9/3/2020 SCO Final Document Submittal Received
2013 | CRI Entrance Improvements |  |  | Updated bdgt: $1,500,000 2,000,000 2500000 | CFWD | Design: 9/16; Const: 8/2018- 12/2018 | 2013-12-05 | 2013-12-05 | 2400000 | √ | 2013-05-16 | 2016-01-26 | 1900000 | 2015-12-18 | √ |  | 2016-01-22 |  | 2016-01-22 | 1900000 | 41526-308 | √ | √ | √ | √ |  | 2016-10-06 | N/A Report only 10/6/2016 | [7 empty] | Estimated at approximately $2.2 Million; Design Start 1/14; Const start 1/15.
2020 | McEniry Chiller Replacement and Electrical Service Upgrades (SCO NAME: Repairs to Electrical, Plumbing, HVAC - McEniry) |  |  | 1093664 | R&R | Design: ; Const: | 2020-09-14 | 2020-09-14 |  | √ | 2021-04-08 | [5 empty] | 2020-09-17 |  |  | 1094000 | 42026-324 | [5 empty] | 2021-04-06 | 2021-04-06 | [7 empty] | Request for ratification of designer selection: Selected - CMTA; 1st - Optima Engineering; 2nd - McKim & Creed
2020 | McEniry Building Roof Replacement |  |  | 804718 | R&R | Design: 6/15/2020; Const: 5/17/2021-7/31/2021 | 2020-09-14 |  |  |  | 2020-08-26 | [5 empty] | 2020-09-17 |  |  |  | 42026-321
2014 | CID II Project - Campus Infrastructure Development - East Village Infrastructure |  |  | $60,330,335.38 $50,830,000; $44,185,000 $46 M $31 M | CID2 |  | 9/22/2020 February 9, 2016 4/2016 Report only; 5/23/2013 | 2013-05-23 | 51,885,037 for John Kirk/Cameron $52,980,000(increase for 2.15 City/NCDOT contribution for John Kirk. $50,830,000; $35 M | √ | 5/21/14 5/13/14 | 2014-06-02 | 46000000 | On hold per Phil's email 1/13/2017 DENIED: 10/21/2016 (SC submitted increase to compensate for East Village Traffic - City contribution 1/15/2014 | √ |  | 2014-02-21 |  | 1/15/2014 | On Hold: $52,980,000 (added $2,150,000); $50,830,000; 4599155 | 41326-307 | [5 empty] | 2014-10-02 | 2014-10-02 | [7 empty] | Estimated at approximately $17.5 M/$35 M
2020 | Kennedy Second Floor Renovation |  |  | 500000 | ITS | [30 empty] | Submitted to Dec 8, 2020 BOT
2020 | McColl Richardson Football Field Turf Replacement |  |  | 500000 | Student Fees-Football Debt | [30 empty] | Submitted to Dec 8, 2020 BOT
2021 | Atkins Library Tower - ADA & Elevator |  |  | 10000000 |  |  | 2021-02-18 | 2021-02-18 | 10000000
2021 | Smith Replace HVAC & Controls, Envelope, Replace Roof |  |  | 5950000 |  |  | 2021-02-18 | 2021-02-18 | 5950000
2021 | Atkins Library Tower - Fire and Smoke Systems |  |  | 3840000 |  |  | 2021-02-18 | 2021-02-18 | 3840000
2021 | Woodward Controls and Lab HVAC Modernization |  |  | 2700000 |  |  | 2021-02-18 | 2021-02-18 | 2700000
2021 | Friday HVAC, Controls, and Electrical Upgrade |  |  | 9700000 |  |  | 2021-02-18 | 2021-02-18 | 9700000
2021 | Sanitary Sewer Easement
Footnote:
N/A = Not Applicable
1. Reported project to board, but no vote by board on project authorization. In some cases the project was reported at the time a designer selection approval was requested.
Another avenue of reporting the project to the trustees was through the Capital Improvements Report at the FPPC meeting.
2. Top # in cell (see CAPSTAT & Code/Item) is most current. Others for historical data only.
Footnote:
A - Project budget reduced by UNCC administration. Decision reported to BOT FPPC via Capital Project update on 1/22/09.
U - University Project under $2M
AP - Advance Planning Authorization

## On-Hold as of 9.2020
|  |  |  | Any Project between 300,000 and 500,000 can go to the BOG before BOT - per Sherry Ceallaigh's conversation with Phil on 3/14/2016 |  |  | REQUEST FOR CAPITAL PROJECT AUTHORIZATION |  |  |  | OC25 SUBMITTAL (REQUIRED TO SCO FOR PROJECTS OVER $2M ONLY) | [10 empty] | HAND OFF |  |  |  |  | REQUEST FOR DESIGNER/CONTRACTOR RATIFICATION/APPROVAL |  |  |  | REQUEST FOR INCREASE IN CAPITAL PROJECT AUTHORIZATION |  |  | DEBT/BOND ISSUANCE APPROVAL | PROJECT COMPLETE | GENERAL INFORMATION
Year | Project | Non-App Project | Approp. Project | Estimate/ Budget | Funding Source (s) | Schedule (CI-1 Form) | Date Approved by BOT FPPC | Dated Approved by Full Board | Budget Approved/ Reported | OC25 Completed but not submitted to SCO | OC25 Sent to SCO | OC25 Approved from SCO | Approved OC25 Amount | Sent to UNC System Office (BOG) | CI-1 | GA to (Gov Ops) BOG | Legislature (BOG Approval) | COS | Interscope Date | Interscope Amount | Code/Item | Scope | P6 Schedule | Cash Flow | Budget (Archibus) | Date | Date Designer/Consultant Approved/Ratified by BOT FPPC | Date Designer/Consultant Approved/Ratified by Full Board | Date Contractor Approved/Ratified by BOT FPPC | Date Contractor Approved/Ratified by Full Board | Date Approved by BOT FPPC | Dated Approved by Full Board | Budget Approved | Date Approved by BOT FPPC/Full Board | After Action Review (AAR) | Notes
2010 | Residence Hall Phase XIII - IN CONSTRUCTION | X |  | 27144956 |  | CCD 7/15 | 2010-12-10 | 2010-12-10 | 27144956 |  | 2010-10-27 | 2010-12-20 | 27145000 | 2012-07-19 | √ | 2012-07-20 | 7/20/2012 |  | 9/11/2012 7/20/2012 | 2,714,500 271,450 | AP 41226/306 | √ | √ |  | √ | 2012-09-18 |  |  | 2013-05-23 | 2013-05-23
2015 | Sycamore Hall Renovation |  |  | 3900000 Auth: $4,200,000/bdgt: $3,900,000 | F & A; R & R | Design 1/2016; Const Start 8/2018-6/2019 | 2015-12-03 | 2015-12-03 | 4000000 | √ | 2016-08-30 | 2016-08-31 | 4200000 | 10/30/2015 9/9/2016 | √ |  | 12/11/2015 10/14/2016 |  | 12/11/2015 10/14/2016 | 420000 4,200,000 | 41526-303 | √ | √ | √ | √ | 2016-02-24 | 2016-10-06 | Report only 10/6/2016
2016 | Parking Lot 8 Expansion |  |  | 475000 $900,000 increase approved 5/24/18 | Parking Receipts | Design: 9/2016; Const.: 10/2018 - 4/2019 | 4/28/2016 | 4/28/2016 | 475000 | √ | 2016-04-04 | n/a | n/a | 4/15/2016 | √ | 2016-05-27 | 5/27/2016 |  | 2016-05-27 | 900000 | 41526-312 |  | √ |  | √ | 2016-06-01 | [9 empty] | Increase was removed from Nov BOT - waiting for AP to complete.
2017 | Residence Hall Phase XVI |  |  | $64,500,00 58500000 | Housing Fund Balance (42%) / Housing Receipts (58%) | Const. 5/14/2018 - 7/2/2022 | 2017-11-28 | 2017-11-28 | 58500000 | √ | 2018-02-27 |  | 58500000 | 2018-02-27 | √ |  | 12/18/2019; 3/23/2018; 12/15/2017 |  | 2017-12-12 | 58500000 | 41726-302 | √ | √ | √ | √ |  | 2018-02-15 | 2018-02-15 | 2018-02-15 | 2018-02-15
2019 | Cameron 2nd Floor Renovation |  |  | 19100000 | CFWD | Design 7/15/2019; Construction 9/1/2020-7/1/2021 | 4/12/2019 Advance Planning | 4/12/2019 Advance Planning | $1,950,000 (only AP is authorized) | √ |  |  |  | 2019-05-21 | √ |  | 2019-05-22 |  | 2019-05-21 | 1950000 | 41826-306 |  | √ |  | √ |  | 2019-10-02
2017 | Student Government Office Renovations |  |  | 1200000 | Student Union Fee Receipts | Cont. 9/29/2019- 1/26/2020 | 2017-11-28 | 2017-11-28 | 1200000 | √ | 2018-02-11 | 2018-02-12 | 1200000 | 2017-12-15 | √ |  | 2017-12-15 |  |  | 1200000 | 41726-305 |  | √
2017 | Student Activity Center (SAC) IT Upgrade |  |  | 1800000 | Excess SAC Debt Fee | Const. 3/2018 - 1/2019 | 2017-02-09 | 2017-02-09 | 1800000 | √ | 2017-03-13 |  |  | 2017-01-13 |  |  | 2017-03-03 |  | 2017-03-03 | 1800000 | 41626-307
2013 | CID II Project E - Academic Complex Renovation |  |  | 21000000 | CID 2B | Design: August 2014; Const.: 12/2016 (Denny first) - 12/2018; Garinger Winningham: 8/2018 - 4/2019 | 2013-05-23 | 2013-05-23 | $21,000,000 approved Interscope amt. | √ | 2014-05-21 | 2014-06-02 | 45580216 |  |  |  | 1/15/2013 (campus infrastructure dev. - multiple programs) |  | 2014-11-18 | 20944000 | 41326-307H | √ | √ | √ | √ |  | 2014-12-04 | N/A | 2016-02-19 | 2016-02-19 | [5 empty] | Approved by the BOG on 1/15/2013 as a part of the Campus Infrastructure Development Phase 2, according to InterScope
2010 | Residence Hall Phase XIII - IN CONSTRUCTION | X |  | 27144956 |  | CCD 7/15 | 2010-12-10 | 2010-12-10 | 27144956 |  | 2010-10-27 | 2010-12-20 | 27145000 | 2012-07-19 | √ | 2012-07-20 | 7/20/2012 |  | 9/11/2012 7/20/2012 | 2,714,500 271,450 | AP 41226/306 | √ | √ |  | √ | 2012-09-18 |  |  | 2013-05-23 | 2013-05-23
2019 | Parking Lot 5A Expansion |  |  | 1000000 | Parking Receipts | Design 1/2020; Construction 4/2020-8/2020 | 2019-10-02 | 2019-10-02 | 1000000 |  |  |  | 1000000 | 2019-11-15 | [5 empty] | 1000000 | 41926-301 |  | √ |  |  |  | 2020-04-02
2016 | West Substation |  |  | 6500000 | CFWD/F & A | Design: 9/16 12/1/16, Const: 3/29/2020 - 3/28/2021 | 2016-02-19 | 2016-02-19 | 6500000 | √ | 2018-08-07 | 2018-08-07 | 6500000 | 1/22/2016 5/23/2018 | √ |  | 3/4/2016; full authorization approved 7/27/18 |  | 2016-03-04 | 6500000 | AP41526-309 | √ | √ | √ | √ | 2016-03-16 | 2016-11-30 | Report only | [7 empty] | Project to be on hold 2021 January

## Inactive or Future Projects
As of 1/1/2014: All closed projects will be hidden on the Capital Projects tab. As of 5/12/2014 all projects that have begun will be hidden. |  |  | Any Project between 300,000 and 500,000 can go to the BOG before BOT - per Sherry Ceallaigh's conversation with Phil on 3/14/2016 |  |  | REQUEST FOR CAPITAL PROJECT AUTHORIZATION |  |  |  | OC25 SUBMITTAL (REQUIRED TO SCO FOR PROJECTS OVER $2M ONLY) | [10 empty] | HAND OFF |  |  |  |  | REQUEST FOR DESIGNER/CONTRACTOR RATIFICATION/APPROVAL |  |  |  | REQUEST FOR INCREASE IN CAPITAL PROJECT AUTHORIZATION |  |  | DEBT/BOND ISSUANCE APPROVAL | PROJECT COMPLETE | GENERAL INFORMATION
Project | Non-App Project | Approp. Project | Estimate/ Budget | Funding Source (s) | Schedule | Date Approved by BOT FPPC | Dated Approved by Full Board | Budget Approved/ Reported | OC25 Completed but not submitted to SCO | OC25 Sent to SCO | OC25 Approved from SCO | Approved OC25 Amount | Sent to GA | CI-1 | GA to (Gov Ops) BOG | Legislature (BOG Approval) | COS | Interscope Date | Interscope Amount | Code/Item | Scope | P6 Schedule | Cash Flow | Budget (Archibus) | Date | Date Designer/Consultant Approved/Ratified by BOT FPPC | Date Designer/Consultant Approved/Ratified by Full Board | Date Contractor Approved/Ratified by BOT FPPC | Date Contractor Approved/Ratified by Full Board | Date Approved by BOT FPPC | Dated Approved by Full Board | Budget Approved | Date Approved by BOT FPPC/Full Board | After Action Review (AAR) | Notes
Arts and Humanities (Future) |  | X | [7 empty] | 2010-10-27 | 2010-12-20 | 102790000
Atkins and Storrs Roof Replacement |  | X | [7 empty] | U 9/29/2010 | U 9/29/2010 | 1035000 | 2010-09-29 | [21 empty] | 2010 6 yr R&R Submitted 9/29/10
Burson Building Modernization & Expansion (Cancel if new Science bldg. approved) |  | X | 34320000 |  |  | 2008-11-13 | 2008-11-13 | 34320000 |  | 10/1/2010 11/3/2008 | 10/28/2010 11/6/2008 | $76,000,000 $67,600,000 | 2010-09-15 | [21 empty] | 6 yr Approp Submittal 9/15/10 / CCD 6/17; moved to CID - not needed due to new science bldg.
Cameron Chemistry Lab - Cancelled as of March 28, 2016 |  |  | 2000000 | Non General |  | ? | [6 empty] | ? |  |  | ? | [18 empty] | CANCELLED as of March 28, 2016
Campus Infrastructure Renewal - Phase 2 (see notes) |  |  | 2000000 |  | Design: 7/2017; Const. 3/2018 | May not be needed (see note) | [28 empty] | Per Tom Sparks, this project will not be needed due to the Science/RUP. However, keep it on the list in case Science/RUP has scope reduction.
New Gardens Greenhouse/Welcome Center (Hold) |  |  | 5000000 |  |  | ?
Parking Deck K - FUTURE | X |  | 27418000 |  |  | 2010-12-10 | 2010-12-10 | 27418000 |  | 2010-10-27 | 2010-12-07 | 27418000
Parking Lot 31 (ON HOLD) | [5 empty] | ON HOLD | [6 empty] | ON HOLD |  |  | ON HOLD
Physical Plant Complex - FUTURE |  | X | 0 | [6 empty] | 2010-10-27 | 2010-12-20 | 36591000
Smith Bldg Modernization - FUTURE |  | X | 0 | [6 empty] | 2010-10-01 | 2010-10-28 | 4355000 | [22 empty] | 2010 6 yr R&R Submitted 9/29/10
Witherspoon Hall Renovation - FUTURE |  |  | 13550000 | [31 empty] | Construction start 5/17.
IT Infrastructure Upgrades Phase 1 (Now part of Science RUP) |  |  | 2500000 |  | Part of Science | Now part of Science increase
Campus Infrastructure Renewal(Atkins/McEniry) |  |  | 1999993 | R & R | Construction: 12/14/17-6/25/18 | 2014-02-28 |  | 2150000 |  |  |  |  | 3/2014 |  |  | 4/2014 |  | 2014-04-11 | 2150000 | 41326-309 | [14 empty] | Increased R & R authorization to include this project funded from FY 13 CFWD. Delayed indefinitely per JF email 8/26/2016
Craver Rd. Hot Water Supply / Return |  |  | 400000 | Carry Forward | [11 empty] | 2017-12-15
Early College High School (ON HOLD) |  |  |  | Gift & NC ECHS Initiative | [30 empty] | Chancellor put the project on hold 1/10/2016
CID II Project - Campus Infrastructure Development |  |  | $60,330,335.38 $50,830,000; $44,185,000 $46 M $31 M | CID2 |  | February 9, 2016 4/2016 Report only; 5/23/2013 | 2013-05-23 | $52,980,000(increase for 2.15 City/NCDOT contribution for John Kirk. $50,830,000; $35 M | √ | 5/21/14 5/13/14 | 2014-06-02 | 46000000 | On hold per Phil's email 1/13/2017 DENIED: 10/21/2016 (SC submitted increase to compensate for East Village Traffic - City contribution 1/15/2014 | √ |  | 2014-02-21 |  | 1/15/2014 | On Hold: $52,980,000 (added $2,150,000); $50,830,000; 4599155 | AP 41326/307 | [5 empty] | 2014-10-02 | 2014-10-02 | [7 empty] | Estimated at approximately $17.5 M/$35 M
Adult Day Care Purchase CANCELLED Remove |  |  | 1300000 | ? | ? | [29 empty] | $1,300,000 reflects 2017 market rate, Chancellor decision not to purchase (RL)
Hawthorn Renovation - ON HOLD | X |  | 9750000 |  | Design 1/15;Const start 5/16; CCD7/17 | 2013-10-10 | 2013-10-10 | 9750000 | √ | 2010-10-27 | 2010-12-07 | 9750000 | 2014-05-20 |  | 2014-06-20 | 2014-06-20 |  | 2014-06-20 | 975000 | AP41326-311 | [14 empty] | Construction start 5/16
Atkins Library Career Center Renovation - ON HOLD as of 3/12/19 |  |  | 2000000 | R & R | Const.: 9/17 - 5/18 |  |  | 2.000,000 | √ | 2016-01-07 | n/a | n/a | 2015-11-16 |  |  | 2015-12-11 |  | 2015-12-11 | 2000000 | 41526-321 |  | √ |  |  |  | 2017-10-11 | 2017-10-11
Energy Projects Phase II |  |  | 1000000 | CFWD | Design 7/1/2019; Construction 1/15/2020-8/15/2020 | 2019-02-19 | 2019-02-19 | 1000000 | √ | 2019-01-24 |  |  | 3/22/19 BOG meeting | √ |  | 2019-03-22 | [5 empty] | √
Fire Sprinkler System Upgrade-Aux Services, Memorial Hall, Cafeteria, Cone |  |  | 0 | [6 empty] | U 10/27/2010 | U 10/27/2010 | 1080000
Colvard Renovation (Formerly Colvard Remaining Projects) |  |  | $1,430,000 $5,090,000 | CFWD 13, 14, CID 2A, 2B; CFWD & F&A | Design: July 2017; Const.: 8/2018 - 6/2020 | 2015-12-03 | 2015-12-03 | 1430000 | √ |  | 2016-01-26 | 1430000 | 2015-12-18 | √ |  | 2016-01-22 |  | 2016-01-22 | 1430000 | AP 41526-306 | [5 empty] | 2014-10-02 | 2014-10-02 | [7 empty] | Removed from CID 2 - 10/2015

## Closed Projects as of 9.2020
|  |  |  | Any Project between 300,000 and 500,000 can go to the BOG before BOT - per Sherry Ceallaigh's conversation with Phil on 3/14/2016 |  |  | REQUEST FOR CAPITAL PROJECT AUTHORIZATION |  |  |  | OC25 SUBMITTAL (REQUIRED TO SCO FOR PROJECTS OVER $2M ONLY) | [10 empty] | HAND OFF |  |  |  |  | REQUEST FOR DESIGNER/CONTRACTOR RATIFICATION/APPROVAL |  |  |  | REQUEST FOR INCREASE IN CAPITAL PROJECT AUTHORIZATION |  |  | DEBT/BOND ISSUANCE APPROVAL | PROJECT COMPLETE | GENERAL INFORMATION
Year | Project | Non-App Project | Approp. Project | Estimate/ Budget | Funding Source (s) | Schedule (CI-1 Form) | Date Approved by BOT FPPC | Dated Approved by Full Board | Budget Approved/ Reported | OC25 Completed but not submitted to SCO | OC25 Sent to SCO | OC25 Approved from SCO | Approved OC25 Amount | Sent to UNC System Office (BOG) | CI-1 | GA to (Gov Ops) BOG | Legislature (BOG Approval) | COS | Interscope Date | Interscope Amount | Code/Item | Scope | P6 Schedule | Cash Flow | Budget (Archibus) | Date | Date Designer/Consultant Approved/Ratified by BOT FPPC | Date Designer/Consultant Approved/Ratified by Full Board | Date Contractor Approved/Ratified by BOT FPPC | Date Contractor Approved/Ratified by Full Board | Date Approved by BOT FPPC | Dated Approved by Full Board | Budget Approved | Date Approved by BOT FPPC/Full Board | After Action Review (AAR) | Notes
2016 | Admissions and Visitors Center |  |  | 7000000 increase: $8,000,000; $7,500,000; 8,000,000; $8,300,000 | Gift (Endowment); Submitted to GA for Non-appropriated on 1/8/2016; Infrastructure Development Fee 12/2017 | Design: 1/1/2016; Const.: 2/2018-4/2019 | 10/2/2015; Increase: Approved 12/2015 by email; ratified on at BOT 2/19/2016 | 10/2/2015; Increase: Approved 12/2015 by email; ratified on at BOT 2/19/2016 | 7000000; $8,000,000 | √ | 2016-09-01 | 2016-09-06 | 8000000 | 9/18/2015; Increase to $8,000,000: 1/2016; Increase to $8,500,000: 12/15/2017 | √ |  | 10/30/2015; 3/4/2016; 12/15/2017 |  | 11/2/2015 ; 3/4/2016 | AP $700,000; 8,000,000 | 41526-302 | √ | √ | √ | √ | 2015-11-12 | 2016-02-19 | 2016-02-19
2019 | Starbucks Renovation |  |  | 485000 | Dining Receipts | Design 12/20/2019; Construction 5/16/2020-7/20/2020 | 2019-10-02 | 2019-10-02 | 700000 |  | 2019-11-20 | [8 empty] | 700000 | 41926-307 |  | √ | [11 empty] | √
2015 | University Recreation Center (HAWC) |  |  | 63500000 | Student Fees; Submitted to GA for Non-appropriated on 1/8/2016 | Design 1/1/2016; Construction 6/2017 - 6/2019 | 4/23/2015 | 2015-04-23 | 66000000 | √ | 2016-01-15 | 2016-01-19 | 66000000 | 2015-04-10 | √ |  | 2015-05-22 |  | 2015-05-22 | 6600000 | AP41426-312 | √ | √ | √ | √ | 2015-05-27 | 2015-10-02 | 2015-10-02 | 2016-02-19 | 2016-02-19 | [5 empty] | Issuance of Debt approved on 4/15/2016 at BOG; BOG 3/6/12-$50,000,000
2017 | Softball Indoor Training Facility |  |  | 650000; 1,150,000 increase requested 1/30/2018; 1,250,000 | Athletic Foundation, Gifts | Design: 6/1/2017 9/6/2017; Const. 12/1/2017 - 4/30/2017 7/2018 - 1/2019 | 2017-04-20 | 2017-04-20 | 650000; 1,150,000 increase requested 1/30/2018 | √ | 1/30/2018; 3/22/2018 | n/a | n/a | 3/21/2017; 3/22/2018 | √ |  | 2017-05-19 |  | 2017-05-22 | 1250000 | 41626-310 | √ | √ | √ | √ | [10 empty] | increase request on 01/30/2018
2018 | Roof Repairs and Replacement - Various Buildings |  |  | 1300000 | R&R | Design 7/1/18; Construction 5/13/2019 - 8/11/2019 | Annual R&R Funds, did not go to BOT | Annual R&R Funds, did not go to BOT | 1300000 | √ | 2018-12-19 | 2018-12-20 | 1300000 | 9/3/2020 Annual R&R Funds, did not go to BOG |  |  | Annual R&R Funds, did not go to BOG |  | 2018-09-11 | 1300000 | 41826-320 | √ | √ | √ | √ |  | 2019-02-19 | [8 empty] | 9/3/2020 - McEniry Roof Replacement RFP Submitted to GA and UNCC Websites
2013 | CID II Project E - Academic Complex Renovation |  |  | 21000000 | CID 2B | Design: August 2014; Const.: 12/2016 (Denny first) - 12/2018; Garinger Winningham: 8/2018 - 4/2019 | 2013-05-23 | 2013-05-23 | $21,000,000 approved Interscope amt. | √ | 2014-05-21 | 2014-06-02 | 45580216 |  |  |  | 1/15/2013 (campus infrastructure dev. - multiple programs) |  | 2014-11-18 | 20944000 | 41326-307H | √ | √ | √ | √ |  | 2014-12-04 | N/A | 2016-02-19 | 2016-02-19 | [5 empty] | Approved by the BOG on 1/15/2013 as a part of the Campus Infrastructure Development Phase 2, according to InterScope

## Closed Projects as of 6.27.18
As of 1/1/2014: All closed projects will be hidden on the Capital Projects tab. As of 5/12/2014 all projects that have begun will be hidden. |  |  | Any Project between 300,000 and 500,000 can go to the BOG before BOT - per Sherry Ceallaigh's conversation with Phil on 3/14/2016 |  |  | REQUEST FOR CAPITAL PROJECT AUTHORIZATION |  |  |  | OC25 SUBMITTAL (REQUIRED TO SCO FOR PROJECTS OVER $2M ONLY) | [10 empty] | HAND OFF |  |  |  |  | REQUEST FOR DESIGNER/CONTRACTOR RATIFICATION/APPROVAL |  |  |  | REQUEST FOR INCREASE IN CAPITAL PROJECT AUTHORIZATION |  |  | DEBT/BOND ISSUANCE APPROVAL | PROJECT COMPLETE | GENERAL INFORMATION
Project | Non-App Project | Approp. Project | Estimate/ Budget | Funding Source (s) | Schedule | Date Approved by BOT FPPC | Dated Approved by Full Board | Budget Approved/ Reported | OC25 Completed but not submitted to SCO | OC25 Sent to SCO | OC25 Approved from SCO | Approved OC25 Amount | Sent to GA | CI-1 | GA to (Gov Ops) BOG | Legislature (BOG Approval) | COS | Interscope Date | Interscope Amount | Code/Item | Scope | P6 Schedule | Cash Flow | Budget (Archibus) | Date | Date Designer/Consultant Approved/Ratified by BOT FPPC | Date Designer/Consultant Approved/Ratified by Full Board | Date Contractor Approved/Ratified by BOT FPPC | Date Contractor Approved/Ratified by Full Board | Date Approved by BOT FPPC | Dated Approved by Full Board | Budget Approved | Date Approved by BOT FPPC/Full Board | After Action Review (AAR) | Notes
ADA Initiative - North Library Lane |  | X | 498000 | Institutional |  | 2014-12-04 | 2014-12-04 | 498000 |  |  |  |  | 2014-11-07 | √ |  | 2014-12-05 |  | 2014-12-05 | 498000 | 41426 - 307 | [14 empty] | Handed off to Design Services
Cafeteria Activites Building | X |  | 2311051 |  |  | 2010-12-10 | 2010-12-10 | 2311051 |  | 2010-10-27 | 2011-02-18 | 2311000 | [13 empty] | 2010-12-10 | 2010-12-10 | [7 empty] | moved to closed tab 6.29.18
CID I Project - Campus Infrastructure Development | X |  | $54,697,500; 49604253 | CID1 |  | 4/2016 - Report only; 12/8/2011 | 2011-12-08 | $54,697,500 49500000 |  | 2011-11-29 | 2012-07-12 | 49500000 | 2011-11-29 |  | 2012-04-13 | 2012-04-13 |  | 2012-07-01 | $54,697,500 49500000 | 41226/301 | [12 empty] | 2012-09-06 |  | 2011 Non App Submittal to GA 11/29/11
CID I Project A - South Village Infrastructure and Loop Road |  |  | 5577271 | CID1 | [7 empty] | N/A 6213000 | [8 empty] | √ | √ |  | √ | √
CID I Project B - South Village Regional Utility Plant (RUP 4) |  |  | 7025000 | CID1 | [7 empty] | N/A 7025000 | [8 empty] | √ | √ |  | √ | √
CID I Project C - Belk Gym - |  |  | 17465000 | CID1 | [7 empty] | $17,456,000 16600000 | [8 empty] | √ | √ |  | √ | 2012-08-08 |  |  | 2013-05-23 | 2013-05-23
CID I Project D - Campus -wide Wi-Fi/Cellular - Connectivity Improvements - |  |  | 3000000 | CID1 | [7 empty] | N/A 3000000
CID I Project - High Voltage & HVAC Misc System Renewal |  |  | 4375000 | CID1 | [7 empty] | $4,375,000 4225000 | [9 empty] | N/A |  | N/A | [10 empty] | these are all Tom Sparks and will not have P6 or Archibus/Sherry Update
CID I Project F - Kennedy Student Collaborative classroom Space and Renovation Completion -COMPLETED |  |  | 1754253 | CID1 | [7 empty] | 1650000 | [9 empty] | √ |  |  | 2013-03-01
CID I Project G - Campus Road Improvements |  |  | 12263034.47 | CID1 |  | 2011-05-26 | 2011-05-26 | 8175000 |  |  | 2012-07-12 | 8272000 | [8 empty] | √ | √ |  | √ | 2012-08-08
CID I Project H - South Village DFAC Bridge Dining Facility Bridge COMPLETE |  |  | 1500000 | CID1 | [7 empty] | 1411955 | [8 empty] | √ | √ |  | √ | NA
CID I Project I - Barnard Roof Replacement Campus Wide Roof Replacement Phase 1 - |  |  | 88023 | CID1 | [7 empty] | $88,045 1500000
CID I Project - Elevator Upgrades (moved from CID 2 in Jan 2016) |  |  | 4100000 | CID 2B | Const: 1/16 - 2/17 | [15 empty] | √ | √ | √ | √ |  | 2014-12-04 | N/A | [7 empty] | Assumed that all above are complete as of 6/27/18 (AR)
Parking Lot 11A Expansion |  |  | 475000 | Parking Receipts | Design: 6/2016; Const.: 7/2016 - 11/2016 | 2016-04-28 |  | 475000 |  |  |  |  | 2016-04-15 | √ | 2016-05-27 | 2016-05-27 |  | 2016-05-27 | 475000 | 41526-311 |  | √ |  | √ | 2016-06-01
SAC Chiller Replacement SAC/Barnard HVAC Chiller Repair SAC HVAC Chiller Replacement |  |  | 750000 |  | Design: Aug 2014; Const.: 12/15 - 9/16 | [15 empty] | √ | √ | √ | √ | √
2015 Repairs & Renovations $775,800
R & R: HVAC & Electrical Repairs - Central Campus |  |  | 425800 | R & R | Design: Feb 2016; Const.: Dec. 2016 |  |  |  | √ | [8 empty] | 2014-07-01 | 425800 | 45591-302 | √ | √ |  | √ | 2015-09-10
R & R: Water Intrusion Repair - Cameron |  |  | 350000 | R & R | Const.: 6/16 - 10/16 |  |  |  | √ | [8 empty] | 2014-07-01 | 350000 | 45591-301 | √ | √ |  | √ | 2015-09-10
Annex Office Upfit (Medical Office Building #2) |  |  | 600000 | R & R | Design: 10/2016; Const.: 7/17 -12/17 |  |  | 600000 | √ | [6 empty] | 2015-12-11 |  | 2015-12-11 | 600000 | 41526-322
Hawthorn Hall Basement Renovation |  |  | 400000 | H&RL Receipts | Design: 2/15/2017; Construction: 5/22/2017 - 8/4/2017 | 2017-04-20 | 2017-04-20 | 400000 |  |  |  |  | 2017-03-21 | √ |  | 2017-05-19 |  |  | 400000
CID II Project - Campus WiFi PH 2 (7 Bldg. Recabling) & Network Cable |  |  | 3,416,148 2,757,000 2,500,000 3000000 | CID 2A/B | Design: Complete; Const.: Current to 8/2017 | [6 empty] | N/A | [8 empty] | √ | √ | √ | √ |  | 2014-10-02 | 2014-10-02
CID II Project - Burson Renovation |  |  | 16743000 $12,990,382 $13,233,382 | CID2A/F&A | Design:1/13; Const.: 8/16 - 9/17 | [15 empty] | √ | √ | √ | √ | 2014-01-12 | 2014-10-02 | 2014-10-02 | 2014-10-02 | 2014-10-02
2013, 14 Repairs & Renovations $6,402,780 | [9 empty] | 2013-09-16 | [5 empty] | 2014-01-10 |  | 2013-07-01 | 4132925 | 41326/320
Cone Switch Gear Relocation |  |  | 380000 | R & R | complete 10/31/18
2015 Repairs & Renovations |  |  | $3,453,900 total | R & R |  | Report to BOT 4/28/2016 | [9 empty] | 2015-12-11 |  | 2015-12-11
R & R 2016
Cone Center HVAC Upgrade |  |  | 1700000 | $853,900 R & R and $846,100 Self-liquidating | Design: 9/2016; Construction: 8/17-2/17 |  |  | 1700000 | √ |  |  |  | R & R; Increase (Self-liquidating) sent to GA 3/4/2016 | √ |  | 12/11/2015; increase with Self-liquidating funds: 4/15/2016 |  | 2015-12-11 | 1,700,000 853900 | 41526-320 | [5 empty] | 2016-11-30 | No. Report only
Student Counseling Center |  |  | 4000000 $4,400,000 | F&A; Institutional Trust Funds | Design Jan 2015; Const 8/2016 - 8/2017 | 12/4/2014; 10/6/2016 | 12/4/2014; 10/6/2016 | 4000000 $4,400,000 | √ | 2016-08-30 | 2016-08-31 | 4000000 | 2016-09-09 | √ |  | 12/5/2014 10/14/2016 |  | 12/5/2014 10/14/2016 | 4000000 $4,400,000 | 41426 - 306 | √ | √ | √ | √ | 2015-01-09 | 2015-04-23 | 2015-04-23
Campus -wide Storm Water (Davis Lake) |  |  | $700,000, $450,000 312000 | Institutional | Design 11/1/14; Const.: 5/2017 - 8/2017 | 4/20/2017; 10/2/2014 | 4/20/2017; 10/2/2014 | $700,000; 450000 | √ | 2014-08-19 |  |  | 4/4/2017; 8/19/2014 | √ |  | 2017-05-19 |  | 2014-09-02 | 700000 | 41426-305 | √ | √ | √ | √
Elm/Maple/Pine Residence Renovations | X |  | $20,405,000; $18,500,000 $17,000,000 $18,500,000 $11,000,000 | HRL | Design: May 2013; Const.: 5/2016 - 7/2017 | Report only 4/28/2016; 4/3/14 12/10/2010 | 2010-12-10 | $20,405,000 reported only; $18,500,000 11000000 | √ | 4/8/2014 10/27/2010 | 2010-12-07 | $18,550,000 $11000000 | 3/11/2016 7/19/2012 | √ | 2/21/14 7/20/2012 | 4/11/2016 7/20/2012 |  | 9/11/2012 7/20/2012 | $20,405,000 1,100,000 110,000 | 41226/307 | √ | √ | √ | √ | 5/7/13; 9/6/2012 | 2013-10-10 | 2013-10-10 | 2013-12-05 | 2013-12-05 | [5 empty] | 6/15 Const. Start; Self liquidating bill 2014
Facilities Operations Building/Complex |  |  | $24,734,893 $20,200,000 $21,298,000 10000000 | Facilities and Administrative & CFWD | Design:8/2016 Const.: 7/2017 - 10/2018 | 2016-04-28 | 2016-04-28 | 21298000 | √ | 2017-04-04 | 2017-04-04 | 24734893 | 1/27/2017 - Increase/Full 4/15/2016 | √ |  | 3/3/2017 5/27/2016 |  | 2016-05-27 | $24,734,893 2.129,800 | AP41526-315 | √ | √ | √ | √ | 2016-05-05 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06
Parking Services Building (Part of FO Complex) |  |  | Included in FO Complex $2,600,000 3000000 | Parking Receipts | Design:8/2016 Const.: 7/2017 - 10/2018 | 2016-04-28 | 2016-04-28 | 3000000 | √ | 2017-04-04 | 2017-04-04 | included in FO | 2016-04-15 | √ | 2016-05-27 | 2016-05-27 |  | 2016-05-27 | 3000000 | 41526-313 | √ | √ |  | √ | 2016-05-05 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06
Parking Lots Revitalization |  |  | 1600000 | Parking Receipts | Design: Current - May 2017; Const: 6/2017 - 1/2018 | 2017-02-09 | 2017-02-09 | 1600000 | √ | 2017-01-04 | n/a | n/a | 2017-01-13 |  |  | 2017-03-03 |  | 2017-03-07 | 1600000 | 41626-306
Residence Dining Hall (Upfit for old dining hall) |  |  | $11,500,000 $10,500,000 9000000 | Housing and Dining Receipts | Design 3/15; Const start 6/16 - 4/2017 | *Increase of $1,000,000 - Beth sending email to FPPC - no need to add to agenda. Increase May 2016; 10/2015; 2/13/2015 | 2/13/2015; 10/2/2015 | $9,000,000; $10,500,000 $11,500,000 | √ | 2015-06-04 | 2015-06-11 | 10500000 | 5/2016 Sherry added increase request of $1,000,000 to Interscope ;5/2015 1/15/2015 | √ |  | 8/2015 2/26/2015 |  | 5/10/2016 2/27/2015 | $11,500,000 $10,500,000 | 41426-310 | √ | √ |  | √ | 2015-03-02 | [9 empty] | *Per Phil's email to Chris on Monday May 9, 2016 at 1:16 p.m. - Title of email: BOT Retreat Agenda Items and Supporting Documents Submittal Schedule
Scott Hall Renovation |  |  | 22500000; $23,200,000 | Housing Receipts; Submitted to GA for Non-appropriated on 1/8/2016 | Design Mar 6/1/2015; Const.: 5/23/17 - 7/2018 12/5/2018 6/1/2017-7/21/2018 | 2015-02-13 | 2015-02-13 | 22500000 | √ | 2015-11-25 | 2015-11-30 | 22500000 | 3/22/2018; 1/15/2015 Non-app list sent approved: 4/15/2016; 5/23/18 | √ |  | 2/27/2015; 2016 Legislative Session, increase approved 7/27/2018 |  | 6/29/2015; 2/27/2015 | AP$2,250,000 - 22,500,000 | AP 41426 - 311A | √ | √ | √ | √ | 2015-01-21 | 2015-10-02 | 2015-10-02 | 2015-10-02 | 2015-10-02 | [5 empty] | Issuance of Debt approved at BOG on 4/15/2016; increase in authorization to $23,200,000 approved by BOG July 2018
Student Union Deck Expansion |  |  | 14500000 | Parking Receipts | Design 6/1/2016; Construction: 5/2017 - 5/2018 | 11/30/2016 4/28/2016 | 11/30/2016 4/28/2016 | $14,500,000 12000000 | √ | 2016-10-14 | 2016-10-19 | 14500000 | 10/14/2016 4/15/2016 | √ |  | 10/28/2016 5/27/2016 |  | 2016-05-27 | $14,500,000 1200000 | 41526-314 | √ | √ | √ | √ | 2016-06-02 | 2016-10-06 | Report only 10/6/2016
Swing Space Phase 1 (Hickory & Cedar) |  |  | 800000 | CFWD15; F & A | Design: Nov 2015; Const.: 6/16 - 10/2016 | 2015-12-03 | 2015-12-03 | 800000 | √ | 2015-09-22 | n/a | n/a | 2015-11-16 | √ |  | 2015-12-11 |  | 2015-12-11 | 800000 | 41526-305 | √ | √ |  | √ | 2015-09-16 | [9 empty] | Formally - CID II Project I - but moved out of CID funding 11/2015
Miltimore-Wallis Roof Replacement |  |  | $400,000 $450,000 | Athletic Foundation | Design: 7/8/2018; Const.: 9/2/2018-11/15/2018 | 2018-10-02 | 2018-10-02 | 450000 | √ | 2018-03-22 | 2018-06-01 | 450000 | 2018-03-22 | √ |  | 2018-05-24 |  | 2018-05-31 | 450000 | 41726-308 | √ | √ | √ | √
Baseball Indoor Training Facility |  |  | 850,000; 1,100,000 approval rec'd 5/24/18 | Athletic Foundation, Gifts | Design: 6/1/2017 9/8/2017; Const. 12/1/2017 - 4/30/2017 3/29/2018 - 8/25/2018 | 2017-04-20 | 2017-04-20 | 850000 | √ | 1/30/2018 3/22/2018 | 2018-03-01 | $850,000; $1,100,000 | 3/21/2017; 03/22/2018 | √√ |  | 2017-05-19 |  | 2017-05-22 | 1100000 | 41626-309 | √ | √ | √ | √ | [10 empty] | increase requested 01/30/2018 3/22/2018
Belk Plaza Revitalization |  |  | 3000000; 1,500,000 | Carry Forward, | Design: 7/1/2016; Const: 9/2017 - 1/2018 | 2015-12-03 | 2015-12-03 | 3000000 | √ | 2015-12-15 | 2016-12-15 | 2000000 | 2015-12-14 | √ |  | 2015-01-22 |  | 2016-01-22 | 3000000 | 41526-307 | √ | √ | √ | √ |  | 2016-10-06 | N/A Report only 10/6/2016
Lab School Renovations |  |  | 1000000 | R&R | Design 12/1/2018; Construction 4/1/2019-8/1/2019 | Annual R&R Funds, did not go to BOT | Annual R&R Funds, did not go to BOT | 1000000 | √ | 2018-09-07 | 2018-09-07 | 1000000 | Annual R&R Funds, did not go to BOT |  |  | Annual R&R Funds, did not go to BOT
Sanford Hall Renovation - | X |  | $30,000,000; $19,000,000 13500000 | HRL | Construction: 5/2020 to 7/2021 | 10/2018; 4/3/14 12/10/2010 | 2012-09-06 | $30,000,000; $19,000,000 13500000 | √ | 2/3/14 10/27/10 | 2/6/14 12/20/2010 | $19,000,000 13500000 | 11/?/18; 9/18/2012 | √ |  | 12/?/2018; 2/21/2014 |  | 2012-09-19 | $30,000,000; $19,000,000;1350000 | 41226/308 | [5 empty] | 2013-10-10 | 2013-10-10 | 2013-12-05 | 2013-12-05 | [5 empty] | 9/19/12 GA approved AP - 6/15 Const. Start; Self liquidating bill 2014
Atkins Air Handler (AHU) |  |  | 1600000 | Carry Forward | Const. 12/2018 - 7/2019 |  |  | 1600000 | √ | 2017-12-12 | 2017-12-12 | 1600000 | 2017-11-03 |  |  | 2017-12-12 |  | 2017-12-13 | 1600000 | 41726-303 | √ | √ | √ | √
Student Activity Center (SAC) IT Upgrade |  |  | 1800000 | Excess SAC Debt Fee | Const. 3/2018 - 1/2019 | 2017-02-09 | 2017-02-09 | 1800000 | √ | 2017-03-13 |  |  | 2017-01-13 |  |  | 2017-03-03 |  | 2017-03-03 | 1800000 | 41626-307
New Warehouse Facilities (SDI, Receiving and Stores, etc.) (?) NOW INCLUDED IN FO COMPLEX |  |  | 2500000 |  | Design: Nov 2016; Const.: Nov2018 | [29 empty] | NOW INCLUDED IN FO COMPLEX
Moore Residence Hall Renovation - | X |  | $28,500,000 15,750,000 |  | Construction: 5/2019 to 7/2020 | 10/2017 10/10/2013 | 2013-10-10 | $28,500,000 15,750,000 | √ | 2010-10-27 | 2010-12-07 | 15750000 | Full Authorization: 11/3/2017; 5/20/2014 |  | 2014-06-20 | 12/15/2017; 6/20/2014 |  | 2014-06-20 | $28,000,000 $2,068,a755 | AP41326-312 | √ | √ | √ | √ |  | 2017-10-11 | 2017-10-11 | [7 empty] | 6/16 Construction Start
Campus Circulation Improvements (Light Rail Complimentary Projects) |  |  | 1000000; $1,400,000 approval rec'd 5/24/18 | Excess CID Debt Fee F & A (Facilities & Administrative Receipts) | Design: 6/13/2016; Constr.: Mar. 8/30/2017 - Jun 2017 12/15/2018 | 2016-02-19 | 2016-02-19 | 1000000 | √ | 2018-03-22 | 2018-03-22 | 1400000 | 1/22/2016 3/22/2018 | √ |  | 2016-03-04 |  | 2016-03-14 | 1000000 | 41526-310 | √ | √ | √ | √ | 2016-03-09
Colvard Renovation (Formerly Colvard Remaining Projects) |  |  | $1,430,000 $5,090,000 | CFWD 13, 14, CID 2A, 2B; CFWD & F&A | Design: July 2017; Const.: 8/2018 - 6/2020 | 2015-12-03 | 2015-12-03 | 1430000 | √ |  | 2016-01-26 | 1430000 | 2015-12-18 | √ |  | 2016-01-22 |  | 2016-01-22 | 1430000 | AP 41526-306 | [5 empty] | 2014-10-02 | 2014-10-02 | [7 empty] | Removed from CID 2 - 10/2015
Fire Sprinkler System Upgrade-Aux Services, Memorial Hall, Cafeteria, Cone |  |  | 0 | [6 empty] | U 10/27/2010 | U 10/27/2010 | 1080000

## Closed Projects Prior to 2014
As of 1/1/2014: All closed projects will be hidden on the Capital Projects tab. | OC25 Submittal (required to SCO for Projects over $2M only) |  |  | Request for Capital Project Authorization |  |  |  |  | Authorization Process | [7 empty] | Request for Designer/Contractor Ratification/Approval |  |  |  | Request for Increase in Capital Project Authorization |  |  | Debt/Bond Issuance Approval | General Information
Capital Project | OC25 Sent to SCO | OC25 Approved from SCO | Approved OC25 Amount | Date Approved by BOT FPPC | Dated Approved by Full Board | Non-Appropriated Project | Appropriated Project | Budget Approved/ Reported | BOT | Sent to GA | Sent to (Gov Ops) BOG | Legislature | COS | CAPSTAT Date | CAPSTAT Amount | Code/Item | Date Designer/Consultant Approved/Ratified by BOT FPPC | Date Designer/Consultant Approved/Ratified by Full Board | Date Contractor Approved/Ratified by BOT FPPC | Date Contractor Approved/Ratified by Full Board | Date Approved by BOT FPPC | Dated Approved by Full Board | Budget Approved | Date Approved by BOT FPPC/Full Board
ARRA Energy Efficiency | [13 empty] | 2010-09-01 | 469600 | 44926/381 | [8 empty] | 5/14/12-CAPSTATE: Funds transferred to close project
Baseball Stadium Improvements |  |  |  | Reported1 | - | X | [10 empty] | - | - | 2006-04-21 | N/A | 2006-04-21 | 2006-04-21 | 6000000 |  | punch list
Cameron Boulevard Expansion |  |  |  | Reported1 | - |  | X | [13 empty] | 2006-04-21 | 2006-04-21 | 1100000 |  | CI-1 for 900,000 5/23/06 - Completed 6/28/07
Campus Master Plan Study | N/A |  |  | 2006-04-21 | 2006-04-21 |  | X | 1000000 | [6 empty] | 1500000 | 40526/308 | 2008-01-31 | 2008-01-31 |  |  |  |  | 1500000
CCB Café/Bookstore Build-Out |  |  |  | 2010-02-05 | 2010-02-05 | X |  | 1000000 | [16 empty] | construction complete 2011
Center City Building | 2006-06-02 | 2006-06-09 | 46093264.9 | Reported1 | - |  | X | [6 empty] | 9/12/2006 9/2006 | 45,827,400 5,582,470 | 40691/301 40726/306 | 2007-02-15 | 2007-02-15 | [6 empty] | construction complete 2011
Center City Building Commissiong Agent |  |  |  | Reported1 | Reported1 |  | X | - | [8 empty] | 2008-01-31 | 2008-01-31 | [6 empty] | construction complete 2011
Central Quadrangle Improvements Study (Advanced Planning) | 2010-12-20 | 4000000 | on hold | 2006-04-21 | 2006-04-21 | X | X | 200000 | [5 empty] | 200000 | 40526/309 | 2010-10-27
CID Project - Phillips Road Realignment | X |  |  |  |  | 2011-05-26 | 2011-05-26 | 5900000
CID Project ? - Campus-wide Road & Embankment Repairs | X |  |  |  |  | 2011-05-26 | 2011-05-26 | 2275000
Colvard Roof Replacement | 2009-08-31 | [12 empty] | 2010-01-20 | 466000 | 40991/302 | [8 empty] | construction complete 2011
Development & Alumni Affairs Center | 2008-08-06 | 2008-09-05 | 3000000
Development Center | 2008-08-05 | 2008-09-09 | 3000000 | 2007-09-06 | 2007-09-06 | X |  | 3000000 | [8 empty] | 2008-06-05 | N/A | [6 empty] | on hold-Church of God
Energy Production & Infrastructure Center (EPIC) | 2008-01-30 | 2008-03-24 | 79023486.96 | 9/6/2007-Reported1 | 9/6/2007-Reported1 | X | X | 76218000 | [5 empty] | 1/6/2009 4/26/2011 8/23/2007 | 52,494,149 25,917,015 19,000,000 | 40891/301 40726/301 40726/301 | 2008-01-31 | 2008-01-31 | 2008-06-05 | 2008-06-05 |  |  |  |  | After Action Mtg - 1/27/2014
Fire Safety Improvements-Hawthorne Hall Sprinkler | [5 empty] | X | [6 empty] | 2008-10-07 | 783,044 1,444,033 | 44891/301
Football Stadium (merged with Football Complex) | 2008-11-03 | 2008-11-04 | 20590000 | 1/22/09-Tabled 2/5/2010 | - | X |  | - | [5 empty] | 2009-01-01 | 200000 | 40826/308 |  | 2009-09-16 | [6 empty] | $6,100 transfer 11/24/09
Football/Sports Complex (Adv Plan) | [13 empty] | 2010-01-20 | 4106100 | 40926/303 | [8 empty] | Gov-Ops approved increase to 4.5 M
Grigg Hall Clean Room | N/A |  |  | 2009-05-29 | 2009-05-29 |  | X | 600000 |  | 2009-05-26 |  |  |  | 2009-08-17 | 600000 | 40826/312 | [8 empty] | CI-1 for $600,000 5/21/09
Hall of Champions |  |  |  | 2007-09-06 | N/A | X |  | 1500000
Harris Alumni Center Parking Lot | 9/22/2008 9/9/2008 | 9/26/2008 ?? | $1,099,999.92 $1,500,000 | 2008-06-05 | 2008-06-05 | X |  | 1050000 | [5 empty] | 2008-11-01 | 1500000 | 40826/305 | [8 empty] | construction complete 2010
Harris Alumni Center Parking Lot (Info Only) |  |  |  | - | - | X |  | 450000
Hunt Village Demo (Student Housing Demolition) | U 10/27/2010 | 750000 | Three demos= $2,000,000 | 2010-05-20 | 2010-05-20 | X |  | 2000000 |  | 2010-09-10 |  |  | 2010-12-07 | 2000000 | 41026/308 | U 10/27/2010 | [8 empty] | Project named: Student Housing Demolition - Three phases
Hunt Village Renovation | 2008-11-03 | 2008-11-04 | 2982978.74
Intercollegiate Tennis Facility | 2008-08-05 | 2008-09-08 | 4000000 | 2008-01-31 | 2008-01-31 |  |  | 4000000 | [5 empty] | 2009-01-02 | 5200000 | 40826/309 | 2009-09-17 | 2009-12-11 | [6 empty] | AAR Meeting held December 6, 2013
Library-SAC Quadrangle Improvements | 2006-06-14 |  | 1500000 | 2006-06-23 | 2006-06-23 |  | X | 900000 | [5 empty] | 2006-09-20 | 1500000 | 40626/306
Martin Village Demo (Student housing Demolition) | U 10/27/2010 | 750000 | Three demos= $2,000,000 | 2010-05-20 | 2010-05-20 | X |  | 2000000 |  | 2010-09-10 |  |  | 2010-12-07 | 2000000 | 41026/308 | U 10/27/2010 | [8 empty] | Project named: Student Housing Demolition - Three phases
Motorsports Building Addition |  |  |  | 2007-06-01 | 6/1/07 Tabled | X |  | 5000000
Motorsports Building II | [13 empty] | 2010-01-20 | 3700000 | 40926/304
Motorsports Building II (Adv Plan) | 8/20/2009 3/18/09 11/3/2008 | 8/28/2009 3/20/2009 11/4/2008 | $4,500,000 $4,000,000 $8,000,000 | 2007-09-06 | 2007-09-06 | X |  | 8000000 $4,000,000A |  | 2009-11-24 | 2010-01-19 |  |  | 2008-09-23 | 4500000 | 40826/304 | 2009-09-17 | N/A | [6 empty] | Request to increase authorization sent to GA 11/24/09 $4.5 M
New Campus Entrance |  | 2007-09-27 | 4000000 | 2004-09-24 | 2004-09-24 | X |  | 3750000 | [6 empty] | 4537500 | 40426/306 | [8 empty] | complete
New Outdoor Rec Facility-Ph II | 2009-03-17 | 2009-03-20 | 6000000
Outdoor Student Recreational Facility | 2008-09-08 | 2008-09-26 | 3999999.95 | 2007-11-01 | 2007-11-01 | X |  | 4000000 | [5 empty] | 2007-10-25 | 7500000 | 40726/304 | 2008-06-05 | N/A |  |  | 2010-05-20 | 2010-05-20 | 7500000
Parking Deck H | 3/17/09 11/3/2008 | 3/20/2009 11/6/2008 | $19,000,000 $14,000,000 | Reported1 | Reported1 | X |  | - | [5 empty] | 7/1/2009 9/1/2005 | 5,000,000 19,000,000 | 40926/301 40526/301 | 2008-06-05 | N/A |  |  | 2008-11-13 | 2008-11-13 | 19000000 | 2009-09-17
Pedestrain Bridge Replacement | [13 empty] | 2010-06-20 | 1500000 | 40926/305 | [8 empty] | construction complete 2010
Phase IX Residence Hall | 2010-10-01 | 2008-05-19 | 39100000 | Reported1 | Reported1 | X |  | 39100000 | [6 empty] | 39100000 | 40526/306 |  |  | 2008-06-05 | 2008-06-05 |  |  |  | 2009-04-16 | construction complete 2011
Prospector Phase II Renovation | 2008-09-09 | 2008-09-19 | 4071159 | Reported1 | Reported1 | X |  | - |  | 2009-02-03 |  |  |  |  | 6800000 | 40626/301 | 2008-06-05 | N/A |  |  | 2008-11-13 | 2008-11-13 | 6100000 |  | construction complete 2011
RDH Renov/Replace | 2010-02-08 | 2010-02-26 | 20330000 | 2010-02-05 | 2010-02-05 | X |  | 20330000 |  | 2010-01-10 | 2010-04-01 |  |  | 2010-08-05 | 20,033,000 2,033,000 | AP 41026/304 |  |  | 2009-04-28 | [5 empty] | duplicate
SAC Offices Renovation | N/A |  |  | 4/16/09 1/22/09-Tabled | 2009-04-16 | X |  | 1000000 | 2009-04-16 | 2009-05-07 |  |  |  | 2009-08-17 | 1000000 | 40826/313 | [8 empty] | CAPSTAT: Funds transferred to close project construction complete 2011
Server Room Installation-CHHS |  |  |  | 2006-06-23 | 2006-06-23 |  | X | 800000 | [12 empty] | 2007-02-15 | 2/15/07-Reported | 1300000
Siding Replacement-Phase III Residence Halls | 2006-07-06 |  | 1100000 | 2006-06-23 | 2006-06-23 | X |  | 1100000 | [16 empty] | Project On Hold
Softball Stadium Seating Improvements | N/A |  |  | 2006-06-23 | 2006-06-23 | X |  | 700000 | [5 empty] | 2006-09-20 | 700000 | 40626/307
South Village Sector Master Plan | [7 empty] | 125000 | [5 empty] | 12/3/2010 8/5/2010 | 338,000 125,000 | 41026/306 | [8 empty] | CI-1 for Increase in Authorization of $213,000 to OSBM 11/17/10
Steam Distribution Phases 3 & 4 | 2010-10-01 | 2010-10-28 | 6857000 | [10 empty] | 2010-09-29 |  | 40826/311 | [8 empty] | 2010 6 yr R&R Submitted 9/29/10
Steam Infrastructure Replacement - Cone & King | N/A |  |  | 2009-05-29 | 2009-05-29 | X |  | 750000 | 2009-05-29 | 2009-06-10 |  |  |  | 2009-08-17 | 750000 | 40826/311 | [8 empty] | CI-1 for $750,000 6/10/09
Student Health Center |  |  |  | Reported1 | - |  | X | [13 empty] | 2006-04-21 | 2006-04-21 | 7865000
Student Union (1) |  |  |  | Reported1 | - |  | X | [13 empty] | 2004-03-05 |  | 45700000
Student Union (2) |  |  |  | - | - |  | X | [13 empty] | 2005-12-02 |  | 59700000
Student Union (3) |  |  |  | - | - |  | X | [6 empty] | 2003-03-21 | 65100000 | 40226/304 | 2003-05-30 | 2003-05-30 | 2006-09-15 | 2006-09-15 | 2007-02-15 | 2/15/07 Reported | 65100000
Student Union (Pedestrian Bridge) Added to SU project |  |  |  | Reported1 | - |  | X | [13 empty] | 2006-04-21 | 2006-04-21 | 1800000 |  | CI-1 for 1,750,000 3/21/06
| OC25 SUBMITTAL (REQUIRED TO SCO FOR PROJECTS OVER $2M ONLY) |  |  | REQUEST FOR CAPITAL PROJECT AUTHORIZATION |  |  | AUTHORIZATION PHASE | [7 empty] | HAND OFF |  |  |  | REQUEST FOR DESIGNER/CONTRACTOR RATIFICATION/APPROVAL |  |  |  | REQUEST FOR INCREASE IN CAPITAL PROJECT AUTHORIZATION |  |  | DEBT/BOND ISSUANCE APPROVAL | GENERAL INFORMATION
Capital Project | OC25 Sent to SCO | OC25 Approved from SCO | Approved OC25 Amount | Date Approved by BOT FPPC | Dated Approved by Full Board | Budget Approved/ Reported | Sent to GA | CI-1 | GA to (Gov Ops) BOG | Legislature (BOG Approval) | COS | CAPSTAT Date | CAPSTAT Amount | Code/Item | Scope | Schedule | Budget (Archibus) | Date | Date Designer/Consultant Approved/Ratified by BOT FPPC | Date Designer/Consultant Approved/Ratified by Full Board | Date Contractor Approved/Ratified by BOT FPPC | Date Contractor Approved/Ratified by Full Board | Date Approved by BOT FPPC | Dated Approved by Full Board | Budget Approved | Date Approved by BOT FPPC/Full Board | Notes
Belk Gym-HVAC & Electrical Upgrades |  |  | 2010-10-27 | 2010-12-20 | 3175000
Belk Gym-Modernization |  |  | 2010-10-27 | 2010-12-20 | 9360000 | [23 empty] | BOG 3/6/12-$65,382,000
Residence Hall Sprinklers-Holshouser, Cedar, Sycamore, Hickory | X | [12 empty] | 2010-01-20 | 300048 | 40991/301 |  |  |  |  | 2009-09-16 | [6 empty] | 2010-02-05 | Holshouser
|  |  | OC25 SUBMITTAL (REQUIRED TO SCO FOR PROJECTS OVER $2M ONLY) |  |  | REQUEST FOR CAPITAL PROJECT AUTHORIZATION |  |  | AUTHORIZATION PHASE | [7 empty] | HAND OFF |  |  |  | REQUEST FOR DESIGNER/CONTRACTOR RATIFICATION/APPROVAL |  |  |  | REQUEST FOR INCREASE IN CAPITAL PROJECT AUTHORIZATION |  |  | DEBT/BOND ISSUANCE APPROVAL | GENERAL INFORMATION
Capital Project | Non-Appropriated Project | Appropriated Project | OC25 Sent to SCO | OC25 Approved from SCO | Approved OC25 Amount | Date Approved by BOT FPPC | Dated Approved by Full Board | Budget Approved/ Reported | Sent to GA | CI-1 | GA to (Gov Ops) BOG | Legislature (BOG Approval) | COS | CAPSTAT Date | CAPSTAT Amount | Code/Item | Scope | Schedule | Budget (Archibus) | Date | Date Designer/Consultant Approved/Ratified by BOT FPPC | Date Designer/Consultant Approved/Ratified by Full Board | Date Contractor Approved/Ratified by BOT FPPC | Date Contractor Approved/Ratified by Full Board | Date Approved by BOT FPPC | Dated Approved by Full Board | Budget Approved | Date Approved by BOT FPPC/Full Board | Notes
Burson (Physical Science Bldg) Sprinkler System |  | X | U 10/27/2010 | U 10/27/2010 | 515000 | [23 empty] | Closed 3/13
Burson HVAC Upgrade |  | X | U 10/1/2010 | U 10/1/2010 | 1773000 |  |  |  | 2010-09-29 | [19 empty] | 2010 6 yr R&R Submitted 9/29/10; Closed 3/13
CARC - Modernize Facilities |  | X | 2008-11-03 | 2008-11-04 | 2800000 | [23 empty] | Closed 3/13
Cedar/Hickory/Sycamore Residence Halls Renovation | X |  | 11/29/2011 10/27/2010 | 5/14/2012 12/7/2010 | $10,000,000 $7,500,000 | 2010-12-10 | 2010-12-10 | 7500000 | 2011-11-29 |  | 2012-04-13 | 2012-04-13 |  | 8/13/2012 7/29/2011 | $10,750,000 $750,000 | 41126/306 41226/303 AP41126/306 |  |  |  |  | 2011-12-08 |  | 2012-09-06 | 2012-09-06 | 9/6/2012; Informed BOT of Cancellation 5/23/13 |  |  | 2012-09-06 | Project cancelled w/BOT 2/13; Need BOT demo approval in 4/14 for Summer '15 Const. Closed 3/13
Colvard Renovation Ph I |  | X | U 10/5/2010 | U 10/5/2010 | 770800 |  |  |  | 2010-10-05 | [19 empty] | 2010 R&R Submitted to GA 10/5/10; Closed 4/13
Cone & East Decks - Repair Walls | X |  | U 10/27/2010 | U 10/27/2010 | 500000 | [23 empty] | Closed 4/13
Emergency Generators - RUP 1 & 2 |  |  | U 10/5/2010 | 2011-06-30 | 1200000 |  |  |  | 2010-10-05 | [19 empty] | Closed 4/13
Fire Sprinkler Sys-14 Residence Halls | X |  | 2008-09-10 | 2008-09-19 | 16146168.86 | 2008-03-28 | 2008-03-28 | 16146169 | [5 empty] | 9/23/2008 1/20/2010 6/7/10 | 16,400,000 300,048 344,614 | 40826/302 40991/301 44891/303 |  |  |  |  | 12/8/11 for Scott 2/17/11 for Moore & Sanford | 9/17/09 for Holshouser, Cedar, Sycamore, & Hickory | 4/26/12-Scott | 4/26/12-Scott |  |  |  | 12/8/11-Scott; 2/17/11-Res Halls-Moore, Sanford; 4/16/09-Res Halls-Hawthorne, Pine, maple & Elm; 2/5/10 Res Halls-Holshouser, Cedar, Sycamore & Hickory | 40991/301 Holshouser; Closed 4/13
Fire Sprinkler System-Oak Hall Student Housing | X |  | N/A |  |  | 2007-11-01 | 2007-11-01 | 800000 | [12 empty] | 2008-01-31 |  |  |  | 2008-09-18 | 2008-09-18 | 1024350 |  | Included in Oak Hall Renovation??; Closed 4/13
Football Complex/Sports Sports Complex | X |  | 2/8/2010 11/3/2008 | 2/26/2010 11/4/2008 | $45,394,000 $24,710,000 | 2/5/2010 1/22/2009 | 2/5/2010 1/22/2009 | $45,393,000 $24,710,000 | 2010-01-27 |  | 2010-04-01 |  |  | 1/21/2009 11/2009 1/1/2009 | 49,894,000 393,900 200000 | 40826/307 41026/301 |  |  |  |  | 2009-09-17 | 2009-09-17 | [5 empty] | 2010-05-20 | Closed 4/13
Hechenbleikner Lake Dam Repair |  | X |  |  |  | 2010-05-20 | 2010-05-20 | 2500000 |  | √ |  |  |  | 2010-04-09 | 2599079 | 40926/306 | [12 empty] | Closed 4/13
Kennedy Bldg Fire Safety |  | X | [11 empty] | 2010-01-20 | 627500 | 40991/303 | [12 empty] | Closed 4/13
Parking Deck I | X |  | 6/10/2010 11/3/2008 | 6/10/2010 11/6/2008 | $28,080,000 $24,480,000 | 2009-01-22 | 2009-01-22 | 24480000 | 2010-01-27 |  | 2010-04-01 | 2009-04-10 | 2009-05-11 | 2/7/2011 6/10/2009 | 29,172,603 29,781,158 1,701,158 | 40826/310 41026/302 |  |  |  |  | 2009-09-17 | 2009-09-17 |  |  | 2010-05-20 | 2010-05-20 | 28080000 | 2011-12-08 | BOG $28,080,000; Closed 4/13
Reese Building HVAC & Electrical Upgrade |  | X | 2010-10-27 | 2010-12-20 | 2035000 | [23 empty] | Closed 4/13
Scott Hall HVAC Repair/Improvements |  | X |  |  |  | 2006-04-21 | 2006-04-21 | 1200000 | 2006-11-10 | [11 empty] | 2006-04-21 | [7 empty] | CI-1 for 1,600,000 11/10/06 Complete; Closed 4/13
•Belk Gym-Roof Replacement |  |  | U 10/27/2010 | U 10/27/2010 | 725000 | [23 empty] | Closed 4/26/13
Electrical Circuit @ CRI | X |  | U 8/31/2010 | U 8/31/2010 | 854000 | 2011-05-26 | 2011-05-26 | 854000 | 2010-10-05 | [19 empty] | 2010 R&R Submittal to GA 10/5/10; Closed 4/26/13
Student Housing Demolition (Demolition of Phase III, Martin Village & Hunt Village) | X |  |  |  | 2010-05-20 | 2010-05-20 | 2000000 | U 10/27/2010 | U 10/27/2010 | 2000000 |  |  | 2010-09-10 |  |  | 2010-12-07 | 2000000 | 41026/308 | [11 empty] | Phase III demo complete 2011